## Testing Tracker
[9 empty] | Cloud IO/DES Source data = Landing Zone, Data validation, Sustainment Plan Prod Delta Lake (not MARS) | Business Owner/ Data Steward Validation | MARS Build Team Unit Testing, Landing zone = Core data DEV & QA Env | MARS Testing, Product Team System Testing (Functional & Non-Functional) Equations, business rules, core, cube = expected results QA Env |  | Maintenance Team Validation QA Env | Maintenance Site(s) SME Validation, Business Acceptance UAT Env
Release | RG | Site | KPI ID # | KPI Category | KPI Sub Category | KPI / Metric | Type | Source System | Data Landing Testing | Validation | Unit Testing | Equation Testing | Business Rule Testing | Pre-UAT | UAT | Release Planned Date | Release Name | Comments
R3 | R1-3 | RDM | RDM-FI-35 | Finance | Plant Standard Operating Metrics | Plant Department Site Cash Production Cost Per Monthly Plant Operating Hours (Actual) | Metric | Gencid | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-31 | D5
R1 | R1-3 | RDM | RDM-ME-12 | Mobile Equipment Avail. | Mobile Equipment Avail. | Box Factor | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
R1 | R1-3 | RDM | RDM-ME-13 | Mobile Equipment Avail. | Mobile Equipment Avail. | Fleet Productivity | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
R1 | R1-3 | RDM | RDM-ME-14 | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-15 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Down Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-16 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Failure Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-17 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Down (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-18 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Failure (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-19 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time To Repair (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-20 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mobile Availability (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-21 | Mobile Equipment Avail. | Mobile Equipment Avail. | Operating Efficiency (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-22 | Mobile Equipment Avail. | Mobile Equipment Avail. | Use of Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-38 | Mobile Equipment Avail. | Mobile SOM | Asset Down Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-39 | Mobile Equipment Avail. | Mobile SOM | Asset Event Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-40 | Mobile Equipment Avail. | Mobile SOM | Asset Failure Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-41 | Mobile Equipment Avail. | Mobile SOM | FMS Total Active Maintenance Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-42 | Mobile Equipment Avail. | Mobile SOM | FMS Total Available Time (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-43 | Mobile Equipment Avail. | Mobile SOM | FMS Total Excluded Calendar Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-44 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Delay Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-45 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-46 | Mobile Equipment Avail. | Mobile SOM | FMS Total Operational Delay Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-47 | Mobile Equipment Avail. | Mobile SOM | FMS Total Production Time (Hours) (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-48 | Mobile Equipment Avail. | Mobile SOM | FMS Total Standby Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | RDM | RDM-ME-49 | Mobile Equipment Avail. | Mobile SOM | FMS Total Utilized Time (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R2 | R1-3 | RDM | RDM-WO/C-45 | Compliance | Compliance | Total Hours (Actual) - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R2 | R1-3 | RDM | RDM-WO/C-86 | Compliance | Compliance | Total Hours (Actual) - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R2 | R1-3 | RDM | RDM-WO/C-4 | Work Order | Work Order | # PMs Scheduled - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R2 | R1-3 | RDM | RDM-WO/C-6 | Work Order | Work Order | # Total Maintenance WO Completed - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R1 | R1-3 | CDA | CDA-ME-12 | Mobile Equipment Avail. | Mobile Equipment Avail. | Box Factor | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
R1 | R1-3 | CDA | CDA-ME-13 | Mobile Equipment Avail. | Mobile Equipment Avail. | Fleet Productivity | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
R2 | R1-3 | RDM | RDM-WO/C-7 | Work Order | Work Order | # Scheduled Maintenance WO - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R5 | R5 | HVC | HVC-ME-38 | Mobile Equipment Avail. | Mobile SOM | Asset Down Count | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-39 | Mobile Equipment Avail. | Mobile SOM | Asset Event Count | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-40 | Mobile Equipment Avail. | Mobile SOM | Asset Failure Count | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-41 | Mobile Equipment Avail. | Mobile SOM | FMS Total Active Maintenance Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-42 | Mobile Equipment Avail. | Mobile SOM | FMS Total Available Time (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-43 | Mobile Equipment Avail. | Mobile SOM | FMS Total Excluded Calendar Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-44 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Delay Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-45 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-33 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Operating Hours to First Down After PM | KPI | Cloud IO <35 days and >35 days | Testing Passed
R1 | R1-3 | CDA | CDA-ME-34 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Down Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
R1 | R1-3 | CDA | CDA-ME-35 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Failure Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
R1 | R1-3 | CDA | CDA-ME-27 | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Department Site Cash Production Cost Per Prod/Aux Operating Hours (Actual) | Metric | Cloud IO <35 days and >35 days
R1 | R1-3 | CDA | CDA-ME-36 | Mobile Equipment Avail. | Mobile Equipment Avail. | Total Down Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
R1 | R1-3 | CDA | CDA-ME-37 | Mobile Equipment Avail. | Mobile Equipment Avail. | Total Failure Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
R5 | R5 | HVC | HVC-ME-46 | Mobile Equipment Avail. | Mobile SOM | FMS Total Operational Delay Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-47 | Mobile Equipment Avail. | Mobile SOM | FMS Total Production Time (Hours) (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-48 | Mobile Equipment Avail. | Mobile SOM | FMS Total Standby Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-49 | Mobile Equipment Avail. | Mobile SOM | FMS Total Utilized Time (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-14 | Mobile Equipment Avail. | Mobile SOM | FMS Maintenance Availability (Actual) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-15 | Mobile Equipment Avail. | Mobile SOM | FMS Mean Down Time (Hours) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-16 | Mobile Equipment Avail. | Mobile SOM | FMS Mean Failure Time (Hours) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-17 | Mobile Equipment Avail. | Mobile SOM | FMS Mean Time Between Down (Hours) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-18 | Mobile Equipment Avail. | Mobile SOM | FMS Mean Time Between Failure (Hours) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-19 | Mobile Equipment Avail. | Mobile SOM | FMS Mean Time To Repair (Hours) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-20 | Mobile Equipment Avail. | Mobile SOM | FMS Mobile Availability (Actual) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-ME-21 | Mobile Equipment Avail. | Mobile SOM | FMS Operating Efficiency (Actual) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R2 | R1-3 | HVC | HVC-WO-1 | Work Order | Work Order | Scheduled Maintenance WO Hours - Mill | Metric | JDE (Maintenance) | Remove | Remove | Remove | Remove | Remove | Remove | Remove | 2022-12-08 | D2 | In Production
R5 | R5 | HVC | HVC-ME-22 | Mobile Equipment Avail. | Mobile SOM | FMS Use of Availability (Actual) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-5 | Plant SOM | Plant Standard Operating Metrics | % Capacity Plant Feed Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed
R5 | R5 | HVC | HVC-PL-5b | Plant SOM | Plant Standard Operating Metrics | % Capacity Plant Production Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | CDA | CDA-PL-44 | Plant | Plant Assay | Recovery % - Cu | KPI | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D6 | Gerry to confirm
R1 | R1-3 | CDA | CDA-ME-14 | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | Site Maintenance Availability calculation in MARS BM (SOM) not matching CDA site maintenance availability calculation. Passed as data matches Wenco. To be explored by site and Maintenance Team. In Production
R1 | R1-3 | CDA | CDA-ME-15 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Down Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-16 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Failure Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-17 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Down (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R2 | R1-3 | HVC | HVC-WO-71 | Compliance | Compliance | Break-in Ratio (duration) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | HVC | HVC-WO-76 | Compliance | Compliance | PM Schedule Compliance (By Duration) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R1 | R1-3 | CDA | CDA-ME-18 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Failure (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R2 | R1-3 | HVC | HVC-WO-78 | Compliance | Compliance | Schedule Compliance (By Duration) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | HVC | HVC-WO-79 | Compliance | Compliance | Schedule Compliance (By Work Order Count) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | HVC | HVC-WO-80 | Compliance | Compliance | Schedule Load (Actual) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Deferred |  |  | Deferred to future release
R2 | R1-3 | HVC | HVC-WO-83 | Compliance | Compliance | Total Break-In Hours (Actual) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | HVC | HVC-WO-85 | Compliance | Compliance | Total Distinct Work Order Count - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | HVC | HVC-WO-86 | Compliance | Compliance | Total Hours (Actual) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | HVC | HVC-WO-88 | Compliance | Compliance | Total Hours (Scheduled) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | HVC | HVC-WO-97 | Compliance | Compliance | Total Non Break-In Hours (Actual) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | HVC | HVC-WO-98 | Compliance | Compliance | Total Non Break-In PM Hours (Actual) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | HVC | HVC-WO-99 | Compliance | Compliance | Total PM Hours (Scheduled) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | HVC | HVC-WO-103 | Compliance | Compliance | Total Work Order Count - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R2 | R1-3 | RDM | RDM-WO/C-13 | Work Order | Work Order | # PMs Scheduled - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R2 | R1-3 | RDM | RDM-WO/C-15 | Work Order | Work Order | # Total Maintenance WO Completed - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R1 | R1-3 | CDA | CDA-ME-19 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time To Repair (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-20 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mobile Availability (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-21 | Mobile Equipment Avail. | Mobile Equipment Avail. | Operating Efficiency (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-22 | Mobile Equipment Avail. | Mobile Equipment Avail. | Use of Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R3 | R1-3 | HVC | HVC-PL-34 | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade | Metric | PARCview | On Hold | [8 empty] | HVC is updating their tags so once complete this can be retested (Two week outage with the site), it will be tested after the Source system is replaced at the HVC site.
R1 | R1-3 | CDA | CDA-ME-38 | Mobile Equipment Avail. | Mobile SOM | Asset Down Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-39 | Mobile Equipment Avail. | Mobile SOM | Asset Event Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-40 | Mobile Equipment Avail. | Mobile SOM | Asset Failure Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | Equation walk through.Operating as expected. Substatus source issue. Substatus not being used. Future meeting with Mario and Erwin to review and address issue In Production
R2 | R1-3 | RDM | RDM-WO/C-16 | Work Order | Work Order | # Scheduled Maintenance WO - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R2 | R1-3 | RDM | RDM-WO/C-44 | Compliance | Compliance | Total Distinct Work Order Count - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R2 | R1-3 | RDM | RDM-WO/C-62 | Compliance | Compliance | Total Work Order Count - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R2 | R1-3 | RDM | RDM-WO/C-85 | Compliance | Compliance | Total Distinct Work Order Count - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R2 | R1-3 | RDM | RDM-WO/C-103 | Compliance | Compliance | Total Work Order Count - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
R3 | R1-3 | RDM | RDM-PL-1 | Plant | Plant Standard Operating Metrics | Effective Asset Utilization | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-2 | Plant | Plant Standard Operating Metrics | Maintenance Availability | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-3 | Plant | Plant Standard Operating Metrics | Mean Down Time (Hours) | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-4 | Plant | Plant Standard Operating Metrics | Mean Time Between Downs (Hours) | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-5 | Plant | Plant Standard Operating Metrics | % Capacity | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | Remove till there is a clarification on the requirement
R3 | R1-3 | RDM | RDM-PL-6 | Plant | Plant Standard Operating Metrics | Physical Availability | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-12 | Plant | Plant Standard Operating Metrics | Daily Production Rate When Running | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-15 | Plant | Plant Standard Operating Metrics | Tonnes Processed (Total Milled in SMT) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-21 | Plant | Plant Standard Operating Metrics | Plant Feed Rate | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-26 | Plant | Plant Downtime | Total Stream Downtime (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-30 | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-31 | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-32 | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | CDA | CDA-ME-41 | Mobile Equipment Avail. | Mobile SOM | FMS Total Active Maintenance Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-42 | Mobile Equipment Avail. | Mobile SOM | FMS Total Available Time (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R3 | R1-3 | RDM | RDM-PL-33 | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-34 | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-35 | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-36 | Plant | Plant Production Metrics | Plant Yield (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-38c | Plant | Plant Production Metrics | Total Metal - Zinc + Lead (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-39c | Plant | Plant Production Metrics | Total Metal - Zinc + Lead (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R1 | R1-3 | CDA | CDA-ME-43 | Mobile Equipment Avail. | Mobile SOM | FMS Total Excluded Calendar Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-44 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Delay Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R3 | R1-3 | RDM | RDM-PL-40 | Plant | Plant Production Metrics | Total ore (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-41 | Plant | Plant Production Metrics | Total ore (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 |  | RDM | RDM-PL-47 | Plant | Plant Standard Operating Metrics | Total Number of Downs | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-48 | Plant | Plant Standard Operating Metrics | Available Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-49 | Plant | Plant Standard Operating Metrics | Calendar Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-50 | Plant | Plant Standard Operating Metrics | Excluded Calendar Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-51 | Plant | Plant Standard Operating Metrics | Maintenance Non Scheduled (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-52 | Plant | Plant Standard Operating Metrics | Maintenance Scheduled (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-53 | Plant | Plant Standard Operating Metrics | Maintenance Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-54 | Plant | Plant Standard Operating Metrics | Major Maintenance Shutdown (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-55 | Plant | Plant Standard Operating Metrics | Operating Delays (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-56 | Plant | Plant Standard Operating Metrics | Production Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-57 | Plant | Plant Standard Operating Metrics | Standby Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-58 | Plant | Plant Standard Operating Metrics | Utilized Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 |  | RDM | RDM-PL-38 | Plant | Plant Production Metrics | Total Metal Zinc (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 |  | RDM | RDM-PL-39 | Plant | Plant Production Metrics | Total Metal Zinc (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-38b | Plant | Plant Production Metrics | Total Metal Lead (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-39b | Plant | Plant Production Metrics | Total Metal Lead (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-23 | Plant | Plant Standard Operating Metrics | Plant Production Rate | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-44a | Plant | Plant Assay | Recovery % - Zn | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-44b | Plant | Plant Assay | Recovery % - Pb | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
R3 | R1-3 | RDM | RDM-PL-13 | Plant | Plant Standard Operating Metrics | Best Daily Production Rate | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | In Production (Should be removed - 23 Feb 2023)
R3 |  | RDM | RDM-PL-5b | Plant | Plant Standard Operating Metrics | % Capacity Plant Production Rate | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | On Hold |  |  | Oriaze to confirm from the Maintenance Team
R3 | R1-3 | CDA | CDA-PL-30 | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R3 | R1-3 | CDA | CDA-PL-31 | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R3 | R1-3 | CDA | CDA-PL-32 | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R3 | R1-3 | CDA | CDA-PL-33 | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R3 | R1-3 | CDA | CDA-PL-34 | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R3 | R1-3 | CDA | CDA-PL-35 | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R3 | R1-3 | CDA | CDA-PL-38 | Plant | Plant Production Metrics | Total Metal (Adjusted) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R3 | R1-3 | CDA | CDA-PL-40 | Plant | Plant Production Metrics | Total ore (Adjusted) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
R3 | R1-3 | RDM | RDM-PL-14 | Plant | Plant Standard Operating Metrics | Number of Maintenance Events | Metric | GenCID | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | Out of Scope
R3 | R1-3 | RDM | RDM-PL-27 | Plant | Plant Downtime | Total Stream Event Count | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Failed |  |  | Source data issue
R2 | R1-3 | RDM | RDM-WO/C-8 | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | Metric | GenCID | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | Source data issue (excel is part of the data required and cannot be ingested). Moving to the backlog to remove from R1-3 deployment will be delivered in a future release. # Scheduled Maintenance WO Completed is blank because this needed to be created in conjunction with a spreadsheet as a source to get weekly schedule which is not available from the source system. You are right to see data for #scheduled maintenance WO and #total maintenance WO completed as those are the count of work orders in scheduled and completed statuses respectively. The combination of both does not give #scheduled maintenance WO completed as this kpi is for work orders that are completed as scheduled, and since we don’t have spreadsheets ingested, this is blank.
R2 | R1-3 | RDM | RDM-WO/C-17 | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mine | Metric | GenCID | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | Source data issue (excel is part of the data required and cannot be ingested). Moving to the backlog to remove from R1-3 deployment will be delivered in a future release. # Scheduled Maintenance WO Completed is blank because this needed to be created in conjunction with a spreadsheet as a source to get weekly schedule which is not available from the source system. You are right to see data for #scheduled maintenance WO and #total maintenance WO completed as those are the count of work orders in scheduled and completed statuses respectively. The combination of both does not give #scheduled maintenance WO completed as this kpi is for work orders that are completed as scheduled, and since we don’t have spreadsheets ingested, this is blank.
R1 | R1-3 | RDM | RDM-ME-33 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Operating Hours to First Down After PM | KPI | Cloud IO <35 days and >35 days | Testing Passed
R1 | R1-3 | CDA | CDA-ME-45 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | RDM | RDM-ME-34 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Down Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
R1 | R1-3 | RDM | RDM-ME-35 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Failure Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
R1 | R1-3 | CDA | CDA-ME-46 | Mobile Equipment Avail. | Mobile SOM | FMS Total Operational Delay Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-47 | Mobile Equipment Avail. | Mobile SOM | FMS Total Production Time (Hours) (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-48 | Mobile Equipment Avail. | Mobile SOM | FMS Total Standby Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | CDA | CDA-ME-49 | Mobile Equipment Avail. | Mobile SOM | FMS Total Utilized Time (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R2 | R1-3 | HVC | HVC-WO-2 | Work Order | Work Order | Scheduled Maintenance WO Hours Completed - Mill | Metric | JDE (Maintenance) | Remove | Remove | Remove | Remove | Remove | Remove | Remove
R2 | R1-3 | HVC | HVC-WO-3 | Work Order | Work Order | Non-scheduled Maintenance WO Hours Completed - Mill | Metric | JDE (Maintenance) | Remove | Remove | Remove | Remove | Remove | Remove | Remove
R2 | R1-3 | HVC | HVC-WO-4 | Work Order | Work Order | # PMs Scheduled - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R2 | R1-3 | HVC | HVC-WO-5 | Work Order | Work Order | # PMs Completed as Scheduled - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R2 | R1-3 | HVC | HVC-WO-6 | Work Order | Work Order | # Total Maintenance WO Completed - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R2 | R1-3 | HVC | HVC-WO-7 | Work Order | Work Order | # Scheduled Maintenance WO - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R2 | R1-3 | HVC | HVC-WO-8 | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R2 | R1-3 | HVC | HVC-WO-9 | Work Order | Work Order | # Non-scheduled Maintenance WO Completed - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R2 | R1-3 | HVC | HVC-WO-77 | Compliance | Compliance | PM Schedule Compliance (By Work Order Count) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R3 | R1-3 | HVC | HVC-PL-30 | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R3 | R1-3 | HVC | HVC-PL-31 | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R3 | R1-3 | HVC | HVC-PL-32 | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R3 | R1-3 | HVC | HVC-PL-33 | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R3 | R1-3 | HVC | HVC-PL-35 | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R3 | R1-3 | HVC | HVC-PL-38 | Plant | Plant Production Metrics | Total Metal (Adjusted) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R3 | R1-3 | HVC | HVC-PL-40 | Plant | Plant Production Metrics | Total ore (Adjusted) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R1 | R1-3 | RDM | RDM-ME-36 | Mobile Equipment Avail. | Mobile Equipment Avail. | Total Down Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
R1 | R1-3 | RDM | RDM-ME-37 | Mobile Equipment Avail. | Mobile Equipment Avail. | Total Failure Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
R3 | R1-3 | RDM | RDM-PL-7 | Plant | Plant Standard Operating Metrics | % Online Time | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R3 | R1-3 | HVC | HVC-PL-44 | Plant | Plant Assay | Recovery % - Cu | KPI | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-22 | Plant SOM | Plant Standard Operating Metrics | Plant Labor Factor (Internal Labor Factor) | KPI | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  |  | Need to Check with Jacob
R5 | R5 | HVC | HVC-PL-17 | Plant SOM | Plant Standard Operating Metrics | Plant Maintenance Internal Labor Hours | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  |  | Need to Check with Jacob
R5 | R5 | HVC | HVC-PL-14 | Plant SOM | Plant Standard Operating Metrics | Number of Maintenance Events | Metric | PARCview | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | Out of Scope
R5 |  | HVC | HVC-PL-15 | Plant SOM | Plant Standard Operating Metrics | Tonnes Processed | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-47 | Plant SOM | Plant Standard Operating Metrics | Total Number of Downs | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-48 | Plant SOM | Standard Time Definitions | Available Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-49 | Plant SOM | Standard Time Definitions | Calendar Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-50 | Plant SOM | Standard Time Definitions | Excluded Calendar Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-51 | Plant SOM | Standard Time Definitions | Maintenance Non Scheduled (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-52 | Plant SOM | Standard Time Definitions | Maintenance Scheduled (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-53 | Plant SOM | Standard Time Definitions | Maintenance Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-54 | Plant SOM | Standard Time Definitions | Major Maintenance Shutdown (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-55 | Plant SOM | Standard Time Definitions | Operating Delays (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-56 | Plant SOM | Standard Time Definitions | Production Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-57 | Plant SOM | Standard Time Definitions | Standby Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-58 | Plant SOM | Standard Time Definitions | Utilized Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-7 | Plant SOM | Plant Standard Operating Metrics | % Online Time | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-45 | Plant SOM | Plant Standard Operating Metrics | Best Daily Feed Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed
R5 | R5 | HVC | HVC-PL-13 | Plant SOM | Plant Standard Operating Metrics | Best Daily Production Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed
R5 | R5 | HVC | HVC-PL-46 | Plant SOM | Plant Standard Operating Metrics | Daily Feed Rate When Running | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-12 | Plant SOM | Plant Standard Operating Metrics | Daily Production Rate When Running | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-1 | Plant SOM | Plant Standard Operating Metrics | Effective Asset Utilization | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-2 | Plant SOM | Plant Standard Operating Metrics | Maintenance Availability | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-3 | Plant SOM | Plant Standard Operating Metrics | Mean Down Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-4 | Plant SOM | Plant Standard Operating Metrics | Mean Time Between Downs (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-6 | Plant SOM | Plant Standard Operating Metrics | Physical Availability | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-21 | Plant SOM | Plant Standard Operating Metrics | Plant Feed Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | HVC | HVC-PL-23 | Plant SOM | Plant Standard Operating Metrics | Plant Production Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 | R5 | RDM | RDM-FI-20 | Finance | Finance Planning | Maintenance Department Site Cash Production Cost (Actual) | Metric | Gencid | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 | R5 | RDM | RDM-FI-2 | Finance | Finance Planning | Plant Department Site Cash Production Cost (Actual) | Metric | Gencid | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 | R5 | RDM | RDM-FI-3 | Finance | Finance General Ledger | Site Cash Production Cost (Actual) | Metric | Gencid | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  |  |  | Requirement is being reviewed, it may need another round of QA process if the requirement changes
R5 | R5 | RDM | RDM-FI-4 | Finance | Finance General Ledger | Total Costs (Actual) | Metric | Gencid | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  |  |  | Requirement is being reviewed, it may need another round of QA process if the requirement changes
R5 |  | RDM | RDM-PL-26-RT | Plant | Plant Downtime | Total Stream Downtime (Hours) | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-27-RT | Plant | Plant Downtime | Total Stream Event Count | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-51-RT | Plant | Plant Standard Operating Metrics | Maintenance Non Scheduled (Hours) | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-52-RT | Plant | Plant Standard Operating Metrics | Maintenance Scheduled (Hours) | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-53-RT | Plant | Plant Standard Operating Metrics | Maintenance Time (Hours) | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-54-RT | Plant | Plant Standard Operating Metrics | Major Maintenance Shutdown (Hours) | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-55-RT | Plant | Plant Standard Operating Metrics | Operating Delays (Hours) | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-57-RT | Plant | Plant Standard Operating Metrics | Standby Time (Hours) | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-47-RT | Plant | Plant Standard Operating Metrics | Total Number of Downs | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | QB2 | QB2-WO/C-30 | Compliance | Compliance | Break-in Ratio (duration) - Mine | KPI | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-34 | Compliance | Compliance | Failure Break-In Ratio - Mine | KPI | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-35 | Compliance | Compliance | Non Failure Break-In Ratio - Mine | KPI | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-36 | Compliance | Compliance | PM Schedule Compliance (By Duration) - Mine | KPI | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-37 | Compliance | Compliance | PM Schedule Compliance (By Work Order Count) - Mine | KPI | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-38 | Compliance | Compliance | Schedule Compliance (By Duration) - Mine | KPI | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-39 | Compliance | Compliance | Schedule Compliance (By Work Order Count) - Mine | KPI | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-40 | Compliance | Compliance | Schedule Load (Actual) - Mine | KPI | Maximo
R5 |  | QB2 | QB2-WO/C-41 | Compliance | Compliance | Schedule Load (Available) - Mine | KPI | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-64 | Compliance | Compliance | Work Index - Mine | KPI | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-65 | Compliance | Compliance | Work Index (Corrected) - Mine | KPI | Maximo
R5 |  | QB2 | QB2-WO/C-18 | Work Order | Work Order | # Non-scheduled Maintenance WO Completed | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-19 | Work Order | Work Order | # Non-Scheduled Maintenance WO Completed due to Failure | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-14 | Work Order | Work Order | # PMs Completed as Scheduled | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-13 | Work Order | Work Order | # PMs Scheduled | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-10 | Work Order | Work Order | Mine Maintenance Internal labor Hours | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-16 | Work Order | Work Order | # Scheduled Maintenance WO | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-17 | Work Order | Work Order | # Scheduled Maintenance WO Completed | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-15 | Work Order | Work Order | # Total Maintenance WO Completed | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-12-MA | Work Order | Work Order | Mine Maintenance other Contractor labor Hours | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-11-MA | Work Order | Work Order | Mine Maintenance Resident Contractor labor Hours | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-24 | Compliance | Compliance | Average Compliance Days - Mine | Metric | Maximo
R5 |  | QB2 | QB2-WO/C-25 | Compliance | Compliance | Average Compliance Meter Hours - Mine | Metric | Maximo
R5 |  | QB2 | QB2-WO/C-42 | Compliance | Compliance | Total Break-In Failure Hours (Actual) - Mine | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-43 | Compliance | Compliance | Total Break-In Hours (Actual) - Mine | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-44 | Compliance | Compliance | Total Break-In Non Failure Hours (Actual) - Mine | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-45 | Compliance | Compliance | Total Distinct Work Order Count - Mine | Metric | Maximo
R5 |  | QB2 | QB2-WO/C-46 | Compliance | Compliance | Total Hours (Actual) - Mine | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-47 | Compliance | Compliance | Total Hours (Available) - Mine | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-48 | Compliance | Compliance | Total Hours (Scheduled) - Mine | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-57 | Compliance | Compliance | Total Non Break-In Hours (Actual) - Mine | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-58 | Compliance | Compliance | Total Non Break-In PM Hours (Actual) - Mine | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-59 | Compliance | Compliance | Total PM Hours (Scheduled) - Mine | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-63 | Compliance | Compliance | Total Work Order Count - Mine | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-49 | Compliance | Item and Trade | Total Item Break-In Cost (Actual) - Mine | Metric | Maximo | [9 empty] | Don to confirm if it can be delivered from Maximo
R5 |  | QB2 | QB2-WO/C-32-MA | Compliance | Item and Trade | Break-in Work (Count) | Metric | Maximo | [8 empty] | D6
R5 |  | QB2 | QB2-WO/C-49-MA | Compliance | Item and Trade | Total Item Break-In Cost (Actual) - Mine | Metric | Maximo
R5 |  | QB2 | QB2-WO/C-50 | Compliance | Item and Trade | Total Item Cost (Actual) - Mine | Metric | Maximo
R5 |  | QB2 | QB2-WO/C-51 | Compliance | Item and Trade | Total Item Cost (Budget) - Mine | Metric | Maximo
R5 |  | QB2 | QB2-WO/C-52 | Compliance | Item and Trade | Total Item Quantity (Actual) - Mine | Metric | Maximo
R5 |  | QB2 | QB2-WO/C-53 | Compliance | Item and Trade | Total Item Quantity (Resource) - Mine | Metric | Maximo | [9 empty] | Will move to D7
R5 |  | QB2 | QB2-WO/C-102-MA | Compliance | Item and Trade | Total Trade Cost (Actual) - Mill | Metric | Maximo
R5 |  | QB2 | QB2-WO/C-103-MA | Compliance | Item and Trade | Total Trade Cost (Budget) - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-71-MA | Compliance | Compliance | Break-in Ratio (duration) - Mill | KPI | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-73-MA | Compliance | Compliance | Compliance Utilization - Mill | KPI | Maximo
R5 |  | HVC | HVC-WO-76-MA | Compliance | Compliance | PM Schedule Compliance (By Duration) - Mill | KPI | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-77-MA | Compliance | Compliance | PM Schedule Compliance (By Work Order Count) - Mill | KPI | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-78-MA | Compliance | Compliance | Schedule Compliance (By Duration) - Mill | KPI | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-79-MA | Compliance | Compliance | Schedule Compliance (By Work Order Count) - Mill | KPI | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-80-MA | Compliance | Compliance | Schedule Load (Actual) - Mill | KPI | Maximo
R5 |  | HVC | HVC-WO-81-MA | Compliance | Compliance | Schedule Load (Available) - Mill | KPI | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-65 | Compliance | Compliance | Average Compliance Days - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-19-MA | Compliance | Compliance | # Non-Scheduled Maintenance WO Completed due to Failure | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-27 | Compliance | Compliance | Average Meter Hours Difference - Mine | Metric | Maximo
R5 |  | HVC | HVC-WO-69 | Compliance | Compliance | Average Target Days - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-69-MA | Compliance | Compliance | Average Target Days - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-72-MA | Compliance | Compliance | Break-in Work (Count) - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-83-MA | Compliance | Compliance | Total Break-In Hours (Actual) - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-84 | Compliance | Compliance | Total Break-In Non Failure Hours (Actual) - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-85-MA | Compliance | Compliance | Total Distinct Work Order Count - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-86-MA | Compliance | Compliance | Total Hours (Actual) - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-88-MA | Compliance | Compliance | Total Hours (Scheduled) - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-97-MA | Compliance | Compliance | Total Non Break-In Hours (Actual) - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-98-MA | Compliance | Compliance | Total Non Break-In PM Hours (Actual) - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-99-MA | Compliance | Compliance | Total PM Hours (Scheduled) - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-103-MA | Compliance | Compliance | Total Work Order Count - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-89 | Compliance | Item and Trade | Total Item Break-In Cost (Actual) - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-48 | Compliance | Item and Trade | Total Item Break-In Cost (Actual) - Mine | Metric | Maximo
R5 |  | HVC | HVC-WO-90 | Compliance | Item and Trade | Total Item Cost (Actual) - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-49 | Compliance | Item and Trade | Total Item Cost (Actual) - Mine | Metric | Maximo
R5 |  | HVC | HVC-WO-91 | Compliance | Item and Trade | Total Item Cost (Budget) - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-50 | Compliance | Item and Trade | Total Item Cost (Budget) - Mine | Metric | Maximo
R5 |  | HVC | HVC-WO-92 | Compliance | Item and Trade | Total Item Quantity (Actual) - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-51 | Compliance | Item and Trade | Total Item Quantity (Actual) - Mine | Metric | Maximo
R5 |  | HVC | HVC-WO-100 | Compliance | Item and Trade | Total Trade Break-In Cost (Actual) - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-59 | Compliance | Item and Trade | Total Trade Break-In Cost (Actual) - Mine | Metric | Maximo
R5 |  | HVC | HVC-WO-101 | Compliance | Item and Trade | Total Trade Cost (Actual) - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-60 | Compliance | Item and Trade | Total Trade Cost (Actual) - Mine | Metric | Maximo
R5 |  | HVC | HVC-WO-102 | Compliance | Item and Trade | Total Trade Cost (Budget) - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-61 | Compliance | Item and Trade | Total Trade Cost (Budget) - Mine | Metric | Maximo
R5 |  | HVC | HVC-WO-9-MA | Work Order | Work Order | # Non-scheduled Maintenance WO Completed - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-5-MA | Work Order | Work Order | # PMs Completed as Scheduled - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-4-MA | Work Order | Work Order | # PMs Scheduled - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-7-MA | Work Order | Work Order | # Scheduled Maintenance WO - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-33-MA | Compliance | Compliance | Failure Break-In Ratio | KPI | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-34-MA | Compliance | Compliance | Non Failure Break-In Ratio | KPI | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-41-MA | Compliance | Compliance | Total Break-In Failure Hours (Actual) | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-42-MA | Compliance | Compliance | Total Break-In Hours (Actual) | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-46-MA | Compliance | Compliance | Total Hours (Available) | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-63-MA | Compliance | Compliance | Work Index | KPI | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-10-MA | Compliance | Compliance | Mine Maintenance Internal labor Hours | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-11-MA | Compliance | Compliance | Mine Maintenance Resident Contractor labor Hours | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-12-MA | Compliance | Compliance | Mine Maintenance other Contractor labor Hours | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-8-MA | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-6-MA | Work Order | Work Order | # Total Maintenance WO Completed - Mill | Metric | Maximo | [8 empty] | D6
R5 |  | HVC | HVC-WO-3-MA | Work Order | Work Order | Non-scheduled Maintenance WO Hours Completed - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-1-MA | Work Order | Work Order | Scheduled Maintenance WO Hours - Mill | Metric | Maximo
R5 |  | HVC | HVC-WO-2-MA | Work Order | Work Order | Scheduled Maintenance WO Hours Completed - Mill | Metric | Maximo
R5 |  | HVC | HVC-FI-20a | Finance | Finance General Ledger | Maintenance Department Site Cash Production Cost (Actual) | Metric | Cost Datamart | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | Out of Scope
R5 |  | HVC | HVC-FI-3a | Finance | Finance General Ledger | Site Cash Production Cost (Actual) | Metric | Cost Datamart | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | Out of Scope
R5 |  | HVC | HVC-FI-1 | Finance | Finance General Ledger | Maintenance Repair Cost (Actual) | Metric | JDE (Cost) | Testing Passed | Testing Passed
R5 |  | HVC | HVC-FI-11 | Finance | Finance Planning | Maintenance Repair Cost (Budget) | Metric | JDE (Cost) | Testing Passed | Testing Passed
R5 |  | HVC | HVC-FI-12 | Finance | Finance Planning | Maintenance Repair Cost (Forecast) | Metric | JDE (Cost) | Testing Passed | Testing Passed
R5 |  | RDM | RDM-PL-5b-RT | Plant | Plant Standard Operating Metrics | % Capacity Plant Production Rate | KPI | RT-DUET | Testing Passed | Testing Passed
R5 | R1-3 | RDM | RDM-PL-5-RT | Plant | Plant Standard Operating Metrics | % Capacity Plant Feed Rate | KPI | RT-DUET | Testing Passed | Testing Passed
R5 | R1-3 | RDM | RDM-PL-7-RT | Plant | Plant Standard Operating Metrics | % Online Time | KPI | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 | R1-3 | RDM | RDM-PL-3-RT | Plant | Plant Standard Operating Metrics | Mean Down Time (Hours) | KPI | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 | R1-3 | RDM | RDM-PL-4-RT | Plant | Plant Standard Operating Metrics | Mean Time Between Downs (Hours) | KPI | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 | R1-3 | RDM | RDM-PL-12-RT | Plant | Plant Standard Operating Metrics | Daily Production Rate When Running | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 | R1-3 | RDM | RDM-PL-13-RT | Plant | Plant Standard Operating Metrics | Best Daily Production Rate | Metric | RT-DUET | Testing Passed | Testing Passed
R5 | R1-3 | RDM | RDM-PL-48-RT | Plant | Plant Standard Operating Metrics | Available Time (Hours) | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 | R1-3 | RDM | RDM-PL-2-RT | Plant | Plant Standard Operating Metrics | Maintenance Availability | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-45-RT | Plant | Plant Standard Operating Metrics | Best Daily Feed Rate | Metric | RT-DUET | Testing Passed | Testing Passed
R5 |  | RDM | RDM-PL-46-RT | Plant | Plant Standard Operating Metrics | Daily Feed Rate When Running | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-14-RT | Plant | Plant Standard Operating Metrics | Number of Maintenance Events | Metric | RT-DUET | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | De-scoped
R5 |  | RDM | RDM-PL-56-RT | Plant | Plant Standard Operating Metrics | Production Time (Hours) | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-6-RT | Plant | Plant Standard Operating Metrics | Physical Availability | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-58-RT | Plant | Plant Standard Operating Metrics | Utilized Time (Hours) | Metric | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R3 |  | RDM | RDM-PL-46 | Plant | Plant Standard Operating Metrics | Daily Feed Rate When Running | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4 | In Production
R5 |  | RDM | RDM-PL-1-RT | Plant | Plant Standard Operating Metrics | Effective Asset Utilization | KPI | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-21-RT | Plant | Plant Standard Operating Metrics | Plant Feed Rate | KPI | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R5 |  | RDM | RDM-PL-23-RT | Plant | Plant Standard Operating Metrics | Plant Production Rate | KPI | RT-DUET | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-03-30 | D5 | In Production
R6 |  | QB2 | QB2-ME-14 | Mobile Equipment Avail. | Mobile SOM | Maintenance Availability (Actual) | KPI | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-15 | Mobile Equipment Avail. | Mobile SOM | Mean Down Time (Hours) | KPI | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-16 | Mobile Equipment Avail. | Mobile SOM | Mean Failure Time (Hours) | KPI | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-17 | Mobile Equipment Avail. | Mobile SOM | Mean Time Between Down (Hours) | KPI | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-18 | Mobile Equipment Avail. | Mobile SOM | Mean Time Between Failure (Hours) | KPI | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-19 | Mobile Equipment Avail. | Mobile SOM | Mean Time To Repair (Hours) | KPI | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-20 | Mobile Equipment Avail. | Mobile SOM | Mobile Availability (Actual) | KPI | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-21 | Mobile Equipment Avail. | Mobile SOM | Operating Efficiency (Actual) | KPI | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-22 | Mobile Equipment Avail. | Mobile SOM | Use of Availability (Actual) | KPI | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-38 | Mobile Equipment Avail. | Mobile SOM | Asset Down Count | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-39 | Mobile Equipment Avail. | Mobile SOM | Asset Event Count | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-40 | Mobile Equipment Avail. | Mobile SOM | Asset Failure Count | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-41 | Mobile Equipment Avail. | Mobile SOM | FMS Total Active Maintenance Hours (Actual) | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-42 | Mobile Equipment Avail. | Mobile SOM | FMS Total Available Time (Actual) | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-43 | Mobile Equipment Avail. | Mobile SOM | FMS Total Excluded Calendar Hours (Actual) | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-44 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Delay Hours (Actual) | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-45 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Hours (Actual) | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-46 | Mobile Equipment Avail. | Mobile SOM | FMS Total Operational Delay Hours (Actual) | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-47 | Mobile Equipment Avail. | Mobile SOM | FMS Total Production Time (Hours) (Actual) | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-48 | Mobile Equipment Avail. | Mobile SOM | FMS Total Standby Hours (Actual) | Metric | Minestar | [8 empty] | D6
R6 |  | QB2 | QB2-ME-49 | Mobile Equipment Avail. | Mobile SOM | FMS Total Utilized Time (Actual) | Metric | Minestar | [8 empty] | D6

## Refactored KPIs
R | RG | Site | KPI ID # | KPI Category | KPI Sub Category | KPI / Metric | Type | Source System | MARS Build Team Unit Testing, Landing zone = Core data DEV & QA Env | MARS Testing, Product Team System Testing (Functional & Non-Functional) Equations, business rules, core, cube = expected results QA Env |  | Maintenance Team Validation UAT Env | Maintenance Site(s) SME Validation, Business Acceptance UAT Env | Comments
R1 | R1-3 | RDM | RDM-ME-12 | Mobile Equipment Avail. | Mobile Equipment Avail. | Box Factor | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
R1 | R1-3 | RDM | RDM-ME-13 | Mobile Equipment Avail. | Mobile Equipment Avail. | Fleet Productivity | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
R1 | R1-3 | RDM | RDM-ME-14 | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | RDM | RDM-ME-15 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Down Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | RDM | RDM-ME-16 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Failure Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | RDM | RDM-ME-17 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Down (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | RDM | RDM-ME-18 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Failure (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | RDM | RDM-ME-19 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time To Repair (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | RDM | RDM-ME-20 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mobile Availability (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | RDM | RDM-ME-21 | Mobile Equipment Avail. | Mobile Equipment Avail. | Operating Efficiency (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | RDM | RDM-ME-22 | Mobile Equipment Avail. | Mobile Equipment Avail. | Use of Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | CDA | CDA-ME-12 | Mobile Equipment Avail. | Mobile Equipment Avail. | Box Factor | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
R1 | R1-3 | CDA | CDA-ME-13 | Mobile Equipment Avail. | Mobile Equipment Avail. | Fleet Productivity | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
R1 | R1-3 | CDA | CDA-ME-14 | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | CDA | CDA-ME-15 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Down Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | CDA | CDA-ME-16 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Failure Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | CDA | CDA-ME-17 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Down (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | CDA | CDA-ME-18 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Failure (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | CDA | CDA-ME-19 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time To Repair (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | CDA | CDA-ME-20 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mobile Availability (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | CDA | CDA-ME-21 | Mobile Equipment Avail. | Mobile Equipment Avail. | Operating Efficiency (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R1 | R1-3 | CDA | CDA-ME-22 | Mobile Equipment Avail. | Mobile Equipment Avail. | Use of Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | HVC | HVC-WO-1 | Work Order | Work Order | Scheduled Maintenance WO Hours - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-2 | Work Order | Work Order | Scheduled Maintenance WO Hours Completed - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-3 | Work Order | Work Order | Non-scheduled Maintenance WO Hours Completed - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-4 | Work Order | Work Order | # PMs Scheduled - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-5 | Work Order | Work Order | # PMs Completed as Scheduled - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-6 | Work Order | Work Order | # Total Maintenance WO Completed - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-7 | Work Order | Work Order | # Scheduled Maintenance WO - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-8 | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-9 | Work Order | Work Order | # Non-scheduled Maintenance WO Completed - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-71 | Compliance | Compliance | Break-in Ratio (duration) - Mill | KPI | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-76 | Compliance | Compliance | PM Schedule Compliance (By Duration) - Mill | KPI | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-77 | Compliance | Compliance | PM Schedule Compliance (By Work Order Count) - Mill | KPI | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-78 | Compliance | Compliance | Schedule Compliance (By Duration) - Mill | KPI | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-79 | Compliance | Compliance | Schedule Compliance (By Work Order Count) - Mill | KPI | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-80 | Compliance | Compliance | Schedule Load (Actual) - Mill | KPI | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-83 | Compliance | Compliance | Total Break-In Hours (Actual) - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-85 | Compliance | Compliance | Total Distinct Work Order Count - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-86 | Compliance | Compliance | Total Hours (Actual) - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-88 | Compliance | Compliance | Total Hours (Scheduled) - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-97 | Compliance | Compliance | Total Non Break-In Hours (Actual) - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-98 | Compliance | Compliance | Total Non Break-In PM Hours (Actual) - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-99 | Compliance | Compliance | Total PM Hours (Scheduled) - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | HVC | HVC-WO-103 | Compliance | Compliance | Total Work Order Count - Mill | Metric | JDE (Maintenance)
R2 | R1-3 | RDM | RDM-WO/C-45 | Compliance | Compliance | Total Hours (Actual) - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-86 | Compliance | Compliance | Total Hours (Actual) - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | HVC | HVC-PL-30 | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | HVC | HVC-PL-31 | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | HVC | HVC-PL-32 | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | HVC | HVC-PL-33 | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | HVC | HVC-PL-34 | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade | Metric | PARCview | [5 empty] | HVC is updating their tags so once complete this can be retested (Two week outage with the site)
R3 | R1-3 | HVC | HVC-PL-35 | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | HVC | HVC-PL-38 | Plant | Plant Production Metrics | Total Metal (Adjusted) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | HVC | HVC-PL-40 | Plant | Plant Production Metrics | Total ore (Adjusted) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-4 | Work Order | Work Order | # PMs Scheduled - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-6 | Work Order | Work Order | # Total Maintenance WO Completed - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-7 | Work Order | Work Order | # Scheduled Maintenance WO - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-8 | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | Metric | GenCID | Remove | Remove | Remove | Remove | Remove | Source data issue (excel is part of the data required and cannot be ingested). Moving to the backlog to remove from R1-3 deployment will be delivered in a future release. # Scheduled Maintenance WO Completed is blank because this needed to be created in conjunction with a spreadsheet as a source to get weekly schedule which is not available from the source system. You are right to see data for #scheduled maintenance WO and #total maintenance WO completed as those are the count of work orders in scheduled and completed statuses respectively. The combination of both does not give #scheduled maintenance WO completed as this kpi is for work orders that are completed as scheduled, and since we don’t have spreadsheets ingested, this is blank.
R2 | R1-3 | RDM | RDM-WO/C-13 | Work Order | Work Order | # PMs Scheduled - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-15 | Work Order | Work Order | # Total Maintenance WO Completed - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-16 | Work Order | Work Order | # Scheduled Maintenance WO - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-17 | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mine | Metric | GenCID | Remove | Remove | Remove | Remove | Remove | Source data issue (excel is part of the data required and cannot be ingested). Moving to the backlog to remove from R1-3 deployment will be delivered in a future release. # Scheduled Maintenance WO Completed is blank because this needed to be created in conjunction with a spreadsheet as a source to get weekly schedule which is not available from the source system. You are right to see data for #scheduled maintenance WO and #total maintenance WO completed as those are the count of work orders in scheduled and completed statuses respectively. The combination of both does not give #scheduled maintenance WO completed as this kpi is for work orders that are completed as scheduled, and since we don’t have spreadsheets ingested, this is blank.
R2 | R1-3 | RDM | RDM-WO/C-44 | Compliance | Compliance | Total Distinct Work Order Count - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-62 | Compliance | Compliance | Total Work Order Count - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-85 | Compliance | Compliance | Total Distinct Work Order Count - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R2 | R1-3 | RDM | RDM-WO/C-103 | Compliance | Compliance | Total Work Order Count - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-1 | Plant | Plant Standard Operating Metrics | Effective Asset Utilization | KPI | GenCID
R3 | R1-3 | RDM | RDM-PL-2 | Plant | Plant Standard Operating Metrics | Maintenance Availability | Metric | GenCID
R3 | R1-3 | RDM | RDM-PL-3 | Plant | Plant Standard Operating Metrics | Mean Down Time (Hours) | KPI | GenCID
R3 | R1-3 | RDM | RDM-PL-4 | Plant | Plant Standard Operating Metrics | Mean Time Between Downs (Hours) | KPI | GenCID
R3 | R1-3 | RDM | RDM-PL-5 | Plant | Plant Standard Operating Metrics | % Capacity | KPI | GenCID
R3 | R1-3 | RDM | RDM-PL-6 | Plant | Plant Standard Operating Metrics | Physical Availability | Metric | GenCID
R3 | R1-3 | RDM | RDM-PL-7 | Plant | Plant Standard Operating Metrics | % Online Time | KPI | GenCID
R3 | R1-3 | RDM | RDM-PL-9 | Plant | Plant Standard Operating Metrics | Plant Department Site Cash Production Cost Per Monthly Plant Operating Hours (Actual) | Metric | GenCID
R3 | R1-3 | RDM | RDM-PL-12 | Plant | Plant Standard Operating Metrics | Daily Production Rate When Running | Metric | GenCID
R3 | R1-3 | RDM | RDM-PL-13 | Plant | Plant Standard Operating Metrics | Best Daily Production Rate | Metric | GenCID
R3 | R1-3 | RDM | RDM-PL-14 | Plant | Plant Standard Operating Metrics | Number of Maintenance Events | Metric | GenCID
R3 | R1-3 | RDM | RDM-PL-15 | Plant | Plant Standard Operating Metrics | Tonnes Processed (Total Milled in SMT) | Metric | GenCID
R3 | R1-3 | RDM | RDM-PL-21 | Plant | Plant Standard Operating Metrics | Plant Feed Rate | KPI | GenCID
R3 | R1-3 | RDM | RDM-PL-26 | Plant | Plant Downtime | Total Stream Downtime (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-27 | Plant | Plant Downtime | Total Stream Event Count | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-30 | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-31 | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-32 | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-33 | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-34 | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-35 | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-36 | Plant | Plant Production Metrics | Plant Yield (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-38 | Plant | Plant Production Metrics | Total Metal (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-39 | Plant | Plant Production Metrics | Total Metal (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-40 | Plant | Plant Production Metrics | Total ore (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-41 | Plant | Plant Production Metrics | Total ore (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | CDA | CDA-PL-30 | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | CDA | CDA-PL-31 | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | CDA | CDA-PL-32 | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | CDA | CDA-PL-33 | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Metric | PIS | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | CDA | CDA-PL-34 | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade | Metric | PIS | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | CDA | CDA-PL-35 | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | CDA | CDA-PL-38 | Plant | Plant Production Metrics | Total Metal (Adjusted) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | CDA | CDA-PL-40 | Plant | Plant Production Metrics | Total ore (Adjusted) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-38b | Plant | Plant Production Metrics | Total Metal Lead (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-39b | Plant | Plant Production Metrics | Total Metal Lead (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-5b | Plant | Plant Standard Operating Metrics | Plant Production Rate | KPI | GenCID
R3 | R1-3 | HVC | HVC-PL-44 | Plant | Plant Assay | Recovery % - Cu | KPI | PARCview | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-44a | Plant | Plant Assay | Recovery % - Zn | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | RDM | RDM-PL-44b | Plant | Plant Assay | Recovery % - Pb | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed
R3 | R1-3 | CDA | CDA-PL-44 | Plant | Plant Assay | Recovery % - Cu | KPI | PIS | Testing Passed | Testing Passed | Testing Passed

## R1-3 Summary
MARS for BM Testing Summary
R1 - 3 KPI Tracking | Current | %
Data Landing Testing | 150 | 147%
Business Owner/ Data Steward Validation | 140 | 137%
Unit Testing | 138 | 135%
Equation Testing | 138 | 135%
Business Rule testing | 138 | 135%
High or Critical Defect - Project/T&I Issue | 0 | 0
High or Critical Defect - Source Data Issue | 0 | 0
Ready for Pre-UAT | 138 | 135%
Pre-UAT | 211 | 207%
UAT | 202 | 198%
Deployed to Production | 12 | 12%
Total KPIs | 102
|  |  | R1 - 3 KPI Tracking | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | Delta
|  |  | Data Landing Testing | 56.73% | 56.73% | 82% | 82% | 82% | 91% | 91% | 91% | 91% | 91% | 91% | 91% | 91% | 91% | 100% | 100% | 100% | 100% | 100% | [6 empty] | 0%
|  |  | Business Owner/ Data Steward Validation | 0% | 0% | 42.31% | 51% | 74% | 82% | 82% | 82% | 82% | 82% | 91% | 91% | 91% | 91% | 91% | 91% | 100% | 100% | 100% | [6 empty] | 0%
|  |  | Unit Testing | 56.73% | 56.73% | 59.62% | 82% | 82% | 82% | 82% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [6 empty] | 0%
|  |  | Equation Testing | 66.35% | 71.15% | 75% | 76% | 76% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [6 empty] | 0%
|  |  | Business Rule testing | 23.08% | 29.81% | 53.85% | 74% | 76% | 77% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [6 empty] | 0%
|  |  | High or Critical Defect - Project/T&I Issue | 14 | 9 | 9 | 3 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0%
|  |  | High or Critical Defect - Source Data Issue | 22 | 17 | 18 | 18 | 18 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0%
|  |  | Ready for Pre-UAT | 0% | 0% | 32.69% | 48% | 50% | 60% | 82% | 82% | 82% | 82% | 91% | 91% | 91% | 91% | 91% | 91% | 100% | 100% | 100% | [6 empty] | 0%
|  |  | Pre-UAT Completed | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 12% | 12% | 34% | 43% | 43% | 70% | 71% | 71% | [6 empty] | 0%
|  |  | UAT Completed | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 12% | 12% | 27% | 27% | 27% | 55% | 55% | [6 empty] | 0%
|  |  | Deployed to Production | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | [6 empty] | 0%
There are 102 KPI's to be delivered for R1-3
|  |  | R1 - 3 KPI Tracking | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28
|  |  | Data Landing Testing | 2022-08-26: 59; 2022-09-02: 59; 2022-09-09: 82
|  |  | Business Owner/ Data Steward Validation | 2022-08-26: 0; 2022-09-02: 0; 2022-09-09: 0
|  |  | Unit Testing | 2022-08-26: 59; 2022-09-02: 59; 2022-09-09: 59
|  |  | Equation Testing | 2022-08-26: 69; 2022-09-02: 74; 2022-09-09: 75
|  |  | Business Rule testing | 2022-08-26: 24; 2022-09-02: 31; 2022-09-09: 53
|  |  | High or Critical Defect - Project/T&I Issue | 2022-08-26: 15; 2022-09-02: 9; 2022-09-09: 9
|  |  | High or Critical Defect - Source Data Issue | 2022-08-26: 23; 2022-09-02: 18; 2022-09-09: 18
|  |  | Ready for Pre-UAT | 2022-08-26: 13; 2022-09-02: 17; 2022-09-09: 0
|  |  | Pre-UAT | 2022-08-26: 0; 2022-09-02: 0; 2022-09-09: 0
|  |  | UAT | 2022-08-26: 0; 2022-09-02: 0; 2022-09-09: 0
|  |  | Deployed to Production | 2022-08-26: 0; 2022-09-02: 0; 2022-09-09: 0
147%
0
-
0
137%
135%
135%
135%
135%
207%
-
198%
-
12%
-
Testing
UAT
Prod
Defects
Data Landing Testing Complete
Data Validated by Business
Unit Testing Complete
Equation Testing Complete
Business Rule Testing Complete
Ready for Pre-UAT
Pre-UAT
UAT
In Production
Defects
Project/T&I Issue
Defects
Source Data Issue
-

## R5 Summary
MARS for BM Testing Summary
R5 KPI Tracking | Current | %
Data Landing Testing | 53 | 98%
Business Owner/ Data Steward Validation | 53 | 98%
Unit Testing | 53 | 98%
Equation Testing | 53 | 98%
Business Rule testing | 53 | 98%
High or Critical Defect - Project/T&I Issue | 3 | 3
High or Critical Defect - Source Data Issue | 0 | 0
Ready for Pre-UAT | 53 | 98%
Pre-UAT | 0 | 0%
UAT | 0 | 0%
Deployed to Production | 0 | 0%
Total KPIs | 54
|  |  | R5 KPI Tracking | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-16 | 2022-12-23 | 2022-12-30 | 2023-01-06 | 2023-01-13 | 2023-01-20 | 2023-01-27 | 2023-02-03 | 2023-02-10 | 2023-02-17 | Delta
|  |  | Data Landing Testing | 54% | 54% | 54% | 43% | 43% | 43% | 43% | 61% | 61% | 61% | 61% | [7 empty] | 0%
|  |  | Business Owner/ Data Steward Validation | 54% | 54% | 54% | 43% | 43% | 43% | 43% | 61% | 61% | 61% | 61% | [7 empty] | 0%
|  |  | Unit Testing | 54% | 54% | 54% | 43% | 43% | 43% | 43% | 61% | 61% | 61% | 61% | [7 empty] | 0%
|  |  | Equation Testing | 0% | 31% | 39% | 30% | 43% | 43% | 43% | 54% | 54% | 54% | 54% | [7 empty] | 0%
|  |  | Business Rule testing | 0% | 31% | 39% | 30% | 43% | 43% | 43% | 54% | 54% | 54% | 54% | [7 empty] | 0%
|  |  | High or Critical Defect - Project/T&I Issue | 0 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [7 empty] | 0%
|  |  | High or Critical Defect - Source Data Issue | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  |  | Ready for Pre-UAT | 0% | 31% | 39% | 30% | 43% | 43% | 43% | 54% | 54% | 54% | 54% | [7 empty] | 0%
|  |  | Pre-UAT Completed | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [7 empty] | 0%
|  |  | UAT Completed | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [7 empty] | 0%
|  |  | Deployed to Production | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [7 empty] | 0%
There are 54 KPI's to be delivered for R5
98%
-
0
-
3
98%
-
98%
-
98%
-
98%
-
98%
-
0%
-
0%
-
0%
-
Testing
UAT
Prod
Defects
Data Landing Testing Complete
Data Validated by Business
Unit Testing Complete
Equation Testing Complete
Business Rule Testing Complete
Ready for Pre-UAT
Pre-UAT
UAT
In Production
Defects
Project/T&I Issue
Defects
Source Data Issue
-

## UAT Summary
Pre-UAT Status
Sum of Count of KPI IDS | Column Labels
| CDA |  | CDA Total | HVC |  | HVC Total | RDM |  | RDM Total | Grand Total
Row Labels | No | Yes |  | No | Yes |  | No | Yes
Compliance and Workorder |  |  |  |  | 23 | 23 |  | 12 | 12 | 35
Fleet | 5 | 4 | 9 |  |  |  | 7 | 2 | 9 | 18
Plant |  | 9 | 9 | 9 |  | 9 | 27 | 4 | 31 | 49
Plant Standard Operating Metrics |  |  |  | 10 |  | 10 |  |  |  | 10
Grand Total | 5 | 13 | 18 | 19 | 23 | 42 | 34 | 18 | 52 | 112
UAT Status
Sum of Count of KPI IDS | Column Labels
| HVC | HVC Total | RDM | RDM Total | Grand Total
Row Labels | Yes |  | Yes
Compliance and Workorder | 1 | 1 | 12 | 12 | 13
Grand Total | 1 | 1 | 12 | 12 | 13

## Pre-UAT & UAT Defects
ID | Open/ Closed | Status | Priority | Release | Created | Type | Category | Related KPI ID | ADO # | Description | Maintanence Team / Site Impact | Actions/Next Steps | RCA Comment
1 | Closed | Fixed & Validated by QA | Critical | D1-RDM 12 | 2022-09-01 | UAT Set-up | UAT Environment |  |  | Access Issue- Sam Can’t Access QA /UAT Environment | Unable to test
2 | Closed | Fixed & Validated by QA | High | D1-RDM 12 | 2022-09-01 | UAT Set-up | UAT Environment |  |  | UAT not available | Testing is occuring in the QA environment. More suseptable to changes | Second QA environment spun up vs. Promotion to UAT
3 | Closed | Fixed & Validated by QA | High | D1-RDM 12 | 2022-09-29 | UAT Set-up | UAT Environment |  |  | View Access Issue-Sam Needs view of Discovery Tables (Raw Data Tables) | Delay in testing/incomplete testing | Sam doing QA not UAT needs Same Access as Abhi for Testing
4 | Closed | Fixed & Validated by QA | Medium | D1-RDM 12 | 2022-10-12 | UAT Set-up | Documentation |  |  | Requirements/ Specification / Data Dictionary not provided to Sam to Complete testing | Delay in testing/incomplete testing | Documents required for Sam to do Pre-UAT not provided
5 | Closed | Fixed & Validated by QA | Medium | D1-RDM 12 | 2022-10-14 | UAT Set-up | Documentation |  |  | KPI/Metrics To be tested not from KPI Catalogue | Delay in testing/incomplete testing | BA provided incorrect KPI List for testing to Sam
6 | Closed | Fixed & Validated by QA | Medium | D1-RDM 12 | 2022-10-17 | UAT Set-up | UAT Environment |  |  | Performance Issues- MARS BM Performance issue ~ 5 min to Run Queries Spec 15 Sec | Delay in testing/incomplete testing | New Data Refresh procedure introduced into UAT directly vs. QA. Owner: Build Team
7 | Closed | Fixed & Validated by QA | High | D1-RDM 12 | 2022-10-18 | UAT Set-up | UAT Environment |  |  | Access Issue -Can’t access Update UAT Environment (UAT MARS TEST V2 (import)​) | Unable to test | ADO Group Conflict Issue resolved by Build Team
8 | Closed | Requirements Gathering | High | Future Deployment | 2022-10-21 10:52 | Enhancement | Crew Code/ Maintenance ID |  |  | Crew code is required but missing. This is currently not available from the source data. NB: There exists AM and PM in the data set for work shifts in Gencid. There's no further crew classification. | Red Dog doesn't have crew codes - they have trade codes. Required by SOM (Source Sam) | BA work required to work with site to have crew code available at RDM Site (and others).
9 | Closed | Fixed & Validated by QA | High | D1-RDM 12 | 2022-10-28 | Defect | Work Orders |  | 599244 | The total work order appears to not be providing the correct results on mine vs mill | Invalid results | Duplicate item
10 | Closed | Requirements Gathering | Medium | D1-RDM 12 | 2022-10-31 | Source Data | Work Orders |  | 600303 | Looks like after the fix (599244), “Other” work orders make up almost 55% of work orders at RDM. | Poor data quality at Source | Stu to follow up with the process to address source data issues.
11 | Closed | Fixed & Validated by QA | High | D1-RDM 12 | 2022-10-31 | Defect | Work Orders |  | 599244 | Total Work Order Count values for Mill and Mine are identical | Poor data quality | Development team to resolve
12 | Closed | Functions as Designed | High | D1-RDM 12 | 2022-10-31 | Investigation | Work Orders |  | 600480 | WO Start Date and WO End Date don’t populate for RDM | Poor data quality | Close - functions as designed
13 | Closed | Requirements Gathering | High | D1-RDM 12 | 2022-10-31 | Source Data | Work Orders |  | 600314 | Seems like # Scheduled Maintenance WOs don’t populate before 2021 and Mine # Scheduled Maintenance WOs seem very low for 2019-2022 | Poor data quality at Source | Oriaze has reviewed Discovery Tables appears to be source data issue. Nicole to validate that the source data not present. Stu to follow up with the process to address source data issues.
14 | Closed | Fixed & Validated by QA | High | D1-RDM 12 | 2022-10-31 | Defect | Work Orders |  | 600272 | Seems like counts of PMs Scheduled is off despite other fields summing correctly. | Invalid results | Reviewed by Oriaze. Conjoin of Workorder and PM required for unique count of PMS. Kirk updated and applied Fix in QA. QA Passed. Promoted to UAT-Failed due to unrelated pipeline issues. Pipleine issue fix deployed. Retest of fix in UAT being performed. Passed by Sharvan for Arjun. Arjun to confirm
15 | Closed | Requirements Gathering | High | D2 or D3-Fleet KPI/Metrics | 2022-11-01 | Defect | Fleet |  | 601255 | Work Shift not working properly-Looks like relationship is to plan not FMS | Invalid results | Not part of Pre-UAT. Need to understand and discuss the business process
16 | Closed | In Progress | Minor (Medium) | Future Deployment | 2022-11-01 | Backlog | Work Orders |  | 601250 | The previous work order status date highlighted doesn’t align with the highlighted wo status date | Invalid results | Assigned to the Build Team
17 | Closed | Deferred | Minor (Medium) | Future Deployment | 2022-11-01 | Backloged | Work Orders |  | Requested | N periods are not working. No Identifier for for break-in work and schedules to check compliance are in spreadsheets so both of these do not apply to RDM work orders | Not Working | Backlog
20 | Closed | Functions as Designed | NA | D1-RDM 12 | 2022-11-01 | Investigation | Work Orders |  | Requested | Slow Process time/Work order ID as slicer | Not Working | Investigated. Works as expected. Oriaze/Arjun to list what slicers work with what KPI/Metrics to proactive communicate expecations to users.
21 | Closed | Fixed | High | D2-HVC | 2022-11-22 | Defect | Work Orders |  | 612222 | CSV missing "898" type in WO | Missing WOs | Oriaze to obtained updated CSV file and build team to upload
22 | Closed | Fixed | Critical | D2-HVC | 2022-11-22 | Defect | Work Orders |  | 612226 | Missing WO that contributed hours (total & scheduled) | Invalid results | Oriaze to update
23 | Closed | Fixed | High | D2-HVC | 2022-11-22 | Defect | Work Orders |  | 612229 | WO 1196101 missing 1 hour work - May 23, 2022 | Invalid results | TBD
24 | Closed | In Progress | Low | D2-HVC | 2022-11-22 | Defect | Work Orders |  | 612233 | Work Orders with 0 actual hours and 0 schedule hours are showing (expected these values would be filtered out) | Invalid results | TBD
25 | Closed | In Progress | High | D3-HVC | 2022-11-22 | Environment | Work Orders |  | Not applicable | JDE Maintenance no longer used at the end of the year | Change in source system | Track this in PI 6. Being tracked in PI 5
26 | Closed | In Progress | Critical | D2-HVC | 2022-11-23 | Environment | Access to the Cube |  | TBD | Unable to access the UAT environment - security was wiped for the dataset. It took awhile for the change to propagate | Unable to test | Determine root cause
27 | Closed | In Progress | Medium | D2-HVC | 2022-11-24 | Source Data issue | Plant Metrics |  | 613064 | Plant metrics at HVC return 0/NaN values from 10/26/2021 to 12/30/2021 | Invalid results | Accepted as-is
28
15
28 | Closed | Invalid |  | D2-CDA | 2022-11-28 | Source Data issue | Plant Metrics |  | NA | Copper Conc Mo Grade % doesn’t populate for the plant assay metrics for CDA | Invalid results | Site error - looking at the wrong report
29 | Closed | Closed |  | D2-CDA | 2022-11-28 | Source Data issue | Plant Metrics |  | 614054 | 10/14/2019 – 12/4/2019 doesn’t populate for any metrics for the plant assay metrics for CDA | Invalid results | Determine root cause
30 |  | Comment | Low | D2-HVC | 2022-11-28 | Source Data issue | Work Orders |  | NA | Break in workorder of 1 hour shown. Supervisor entered in the wrong line. Logic should show that if line items in the Time Entry File have all the same Date, Shift, Supervisor, and Work Order Number, then the scheduled hours can be summed, and the actual hours can be summed for those matching line items. |  | Captured as a comment, no action is required
31 | Open | In Progress | High | D2 - CDA | 2022-12-02 | Defect | Plant Assay | CDA-PL-44 | 615766 | Metric Fail CDA-PL-44 Recovery % CU not matching site reports | Invalid results | Site has a different formula than standard/other sites. Action to review with Maintenance Team Stu to followup with the Maintenance team on Oriaze's email. ETA - Jan 10 Sites need to decide whether they want this Metric as Standard metric or not.
32 | Open | In Progress | Medium | D2- CDA | 2022-12-02 | Defect | Plant Assay |  | 615769 | Refresh MARS Daily refresh time is not optimized (3:00 AM- 6:00 AM MST) with Site Shift Schedule | Invalid results | Future release - needs to go in to the backlog
33 |  | Comment | Medium | D2- CDA | 2022-12-02 | Feedback | Plant Assay |  | NA | Translation of Metrics/KPI to Spanish. Planed as a future enhancement. In-term may be able to enter the Spanish name in the Description field | Null | Captured as a comment, future plan
34 |  | Comment | Medium | D2- CDA | 2022-12-02 | Feedback | Plant Assay |  | NA | Documentation Request to know PIS system Tags that are being used for the Metric. Where do they find without consulting Oriaze? E.g. Option put in the Description Field or Other Coms material. | Null | Captured as a comment
35 |  | Comment | Low | D2- CDA | 2022-12-02 | Feedback | Plant Assay |  | NA | Field Name Change Requested (include CU in name). MARS BM Field Name (MARS-BM Table] RE: “Plant Assay Metrics'[zinc_tails_flag]” Zinc flag refers to Copper and Zinc Flag recommendation name be change to reflect metric e.g “CuZn_tails_flag”. Caused confusion/time to confirm that Zinc tails flag included Copper. | Null | Address in Refactor Work-Already being address (TBC)
36 |  | Comment | Low | D2- CDA | 2022-12-02 | Feedback | Plant Assay |  | NA | Metric Name may require change. “Copper Tails Grade %” in MARS BM Tool and Data Dictionary not matching KPI/Metric Name in KPI Catalogue/Testing “Copper Tails Grade (Zinc Tails Grade)”. Currently different names in different documents cause confusion.Also, Metric refers to Cu and Zn % depending on Site e.g. Copper tails grade (Zn grade) % might be a better name. Less preferred option list Zinc in description field. | Null | Oriaze to inform of name updates.
37 | Closed | In Progress | High |  | 2022-12-16 | Defect | FMS |  | 624320 | FMS Model issue. Status code is partially blank for all the equipments for every month from 2020 | Null | Kirk believes that it is a model issue.
38 | Closed | In Progress | High |  | 2022-12-16 | Environment | UAT Environment |  | TBC | Gerry is unable to access 7 metrics for RDM - UAT. Values are coming up blank. | Null | Kirk to investigate
39 | Closed | Resolved | Medium |  | 2022-12-16 | Feedback | Documentation |  | TBC | Need to determine how to respond to UAT testers on clarifications of KPI/metric deifinitions | Null | Kirk and Gerry to work together to get the definitions
40 | Closed | Resolved | High |  | 2022-12-19 | Defect | FMS |  | 625143 | Phantom hours showing up in RDM Mobile for equipment not running during specific times |  | Resolved
41 | Closed | In Progress | Low |  | 2022-12-20 | Defect | FMS |  | 625527 | Mean Time Between Down(Hours) is showing blank screen in Pre-UAT. |  | Need to verify with Oriaze to modify the requirement document with comment that Status Codes should be considered for this KPI, hence left the defect open
42 | Closed | In Progress | Low |  | 2022-12-20 | Defect | FMS |  | 625529 | Mean Time Between Failure(Hours) is showing blank screen in Pre-UAT. |  | Need to verify with Oriaze to modify the requirement document with comment that Status Codes should be considered for this KPI, hence left the defect open
42 | Closed | Closed | High |  | 2022-12-22 | Defect | FMS | RDA-ME-16/CDA-ME-16 | 626804 | RDA-ME-16/CDA-ME-16: The calculation for Unscheduled Total Maintenance Hours(Actual) is not consistent. |  | Resolved
43 | Closed | Resolved | High |  | 2022-12-22 | Defect | Plant Assay | HVC-PL-30/HVC-PL-32 | 626836 | HVC-PL-30/HVC-PL-32: HVC - Two Plant Assay Metrices are not visible in Pre-UAT |  | Resolved
44 | Closed | Resolved | High |  | 2023-01-05 | Defect | Plant SOM | RDM-PL-7 | 630915 | %Online Time is showing lots of NaN values |  | Resolved
45 | Closed | Resolved | High | D4-CDA | 2023-01-09 | Defect | FMS |  | 631600 | Pre-UAT : FMS: CDA : The Month Date filter goes blank after selecting the site as CDA |  | Resolved
46 | Closed | In Progress | High | D3-CDA | 2023-01-09 | Defect | FMS |  | 631650 | Pre-UAT - FMS: RDM-ME-21: FMS Operating Efficiency is blank for some equipment
47 | Closed | Resolved | Medium | D3-RDM | 2023-01-17 | Defect | FMS |  | 635394 | Pre-UAT ¦ RDM showing some Spanish equipment type |  | Resolved
48 | Closed | Resolved | High | D3-RDM | 2023-01-20 | Defect | FMS | RDM-ME-22 | 637798 | UAT - The Use of Availability(Actual) va;ue does not match with the report for the date 2022-11-16 | Error | Resolved
49 | Closed | Resolved | High | D4-HVC | 2023-01-24 | Defect | Plant SOM |  | 639990 | Pre-UAT - HVC Plant SOM : The KPIs/Metrics are not visible in Pre-UAT cube in Power BI |  | Resolved
50 | Closed | Resolved | High | D4-HVC | 2023-01-24 | Defect | Plant Assay | HVC-PL-30 | 640014 | UAT - No data showing for user: Frank Laroche for HVC-PL-30 |  | Issue resolved
51 | Closed | Resolved | High | D4-HVC | 2023-01-27 | Comment | Plant SOM |  |  | HVC-PL-5b is missing from the KPI Catalog.
52 | Closed | Resolved | Critical | D4-HVC | 2023-01-31 | Defect | Plant Assay & Plant Production |  | 643901 | HVC Plant Assay and Plant Production KPIs/Metrics are not showing up in UAT environment | Cannot proceed with UAT | Closed
53 | Closed | Resolved | High | D4-HVC | 2023-01-31 | Defect | Plant Assay | HVC-PL-33 | 643911 | Copper Conc Mo Grade ppm is not a valid Metric for HVC. It should be Copper Conc Mo Grade % for HVC. | Invalid Metric | Resolved
54 | Closed | Fixed | High | D3-RDM | 2023-02-02 | Defect | Plant SOM |  | 645847 | Production: Mapping Error on Ball Mill/Isamill | Incorrect mapping | With Test team to test | No requirement specification, so missed Testing
55 | Closed | Resolved | High | D4-RDM | 2023-01-30 | Defect | Finance | RDM-PL-9 | 643106 | UAT: RDM Finance : Plant Department Site Cash Production Cost Per Operating Hours (Actual) is not showing data | Showing no value | Issue resolved
62 | Open | New | Low |  | 2023-01-05 | Defect | HVC Plant Assay |  | 630703 | Pre - UAT - HVC-PL-34 : Plant Assay : Copper Conc Insol Grade is showing 0 value for Nov 2021 to Dec 2021 and then Feb 2022 to Dec 2022 | No value shows for some time duration | Future work
57 | Closed | Resolved | High | D4-HVC | 2023-02-03 | Defect | HVC |  | 648055 | Pre-UAT : HVC Plant SOM: The Month Year filter is going blank as soon as HVC site is selected | Calendar is not working for HVC | Issue resolved | Dimensions are not clearly mentioned in requirement and code changed along with time
56 | Closed | Resolved | Medium | D4-CDA | 2023-02-02 | Defect | CDA FMS |  | 645826 | UAT and Pre-UAT : Some of the CDA FMS KPIs/Metrics are showing slight different values in UAT compared to Pre-UAT. | Showing slight different value in Pre-UAT compared to UAT | With Test team to test | The data was not at per in Pre-UAT compared to UAT
59 | Closed | Resolved | High | D4-HVC | 2023-02-08 | Defect | HVC FMS |  | 651498 | FMS Data showing NULL instead of Unknown |  | Issue resolved | Missing requirement
60 | Closed | Resolved | Medium | D4-HVC | 2023-02-08 | Defect | HVC FMS |  | 653361 | HVC FMS ¦ Production Time, Utilized Time, Standby Time, Available Time and Operating Delays Power BI Values are not matching with Site Values for CAT793F,CAT793F and CAT793C | Invalid results | Issue is resolved | QA defect
61 | Closed | Resolved | Medium | D4-HVC | 2023-02-08 | Defect | HVC FMS |  | 653367 | HVC FMS ¦ System Dimension (FMS Name) is missing in the cube | System Names from the KPIs/Metrics are missing | Issue is resolved | QA defect
58 | Closed | Closed | Low | D4-HVC | 2023-02-03 | Defect | HVC Plant SOM |  | 648109 | Pre-UAT : HVC Plant SOM: Production Time, Utilized Time and Available Time are showing negative values. | Negative values | Data for three dates are showing negative(Aug 15, 2021, Nov 28, 2022, Dec 7, 2022). This is a bad data issue at the source | Something changed moving the code after QA functional testing to Pre-UAT
63 | Closed | Resolved | High | D4-HVC | 2023-02-10 | Defect | HVC Plant SOM | HVC-PL-5 and HVC-PL-5b | 654219 | HVC Plant SOM: % Capacity Plant Feed Rate and % Capacity Plant Production Rate are showing more than 100% value | Showing >100% values | The defect is resolved in the 654219 cube. It needs to be promoted to the next environment. | Missing requirement to validate KPIs with different sites/All sites together
64 | Closed | Resolved | High | D4-HVC | 2023-02-10 | Defect | HVC Plant SOM |  | 654241 | HVC Plant SOM: Mean Down Time (Hours) and Mean Time Between Downs (Hours) are showing NaN and Infinity for some days. | Invalid results | With Build Team | Missing requirement to validate KPIs with different dates in a month
65 | Closed | Resolved | High | D4-RDM | 2023-02-15 | Defect | RDM Finance | RDM-PL-9 | 656301 | Pre-UAT: The logic for Plant Department Site Cash Production Cost Per Operating Hours (Actual) is changed | Invalid results | Resolved | DAX clean up was not done and also a miss from QA
66 | Closed | Completed | High | D4-HVC |  | Comment | HVC Plant SOM | HVC-PL-4 |  | HVC Plant SOM requirement needs to be updated with the Auto Mills filter for Mean Time Between Downs(Hours). | Invalid results | Done | Missing requirement
67 | Closed | Resolved | High | D4-HVC | 2023-02-16 | Defect | HVC Plant SOM | HVC-PL-52 and HVC-PL-54 | 657058 | UAT: HVC Plant SOM: Major Maintenance Shutdown and Maintenance Scheduled | Invalid results | Issue is fixed | Missing requirement and Specification document
68 | Closed | Resolved | Critical | D4-HVC | 2023-02-17 | Defect | HVC FMS | HVC-ME-39 | 657324 | UAT: Asset Event Count (HVC FMS) is duplicate | Invalid result | With Build Team | Missing specification document
69 | Closed | Resolved | Critical | D4-HVC | 2023-02-17 | Defect | HVC FMS | HVC-ME-20, HVC-ME-21, HVC-ME-22 | 657272 | UAT: HVC FMS: Physical Availability, Use of Availability and Operating Efficiency (HVC FMS) don't match with the site report | Invalid result | With Build Team | Missing requirement and Site Report document
70 | Closed | Resolved | Critical | D4-HVC | 2023-02-17 | Defect | HVC FMS | HVC-ME-46, HVC-ME-47, HVC-ME-48 | 657243 | UAT: HVC FMS: The hours are off for Production Time, Operational Delay, Standby Time (HVC FMS) | Invalid result | With Build Team | Missing requirement and Site Report document
71 | Closed | Resolved | Critical | D4-HVC | 2023-02-17 | Defect | HVC FMS | HVC-ME-47 | 657225 | UAT: HVC FMS: Production Time Hours Exist Where There Shouldn't Be (HVC FMS) | Invalid result | Issue resolved | Missing requirement and Site Report document
72 | Closed | Resolved | Medium | D4-HVC | 2023-02-17 | Defect | HVC FMS |  | 657169 | UAT ¦ Discovery tables are missing in UAT Synapse | Missing source table in the Synapse | Issue resolved | QA found this issue during smoke testing
73 | Closed | Cancelled | High | D4-HVC | 2023-02-21 | Defect | HVC Finance | HVC-FI-2 | 658343 | UAT: RDM-FI-2: Plant Department Site Cash Production Cost (Actual) is showing different value compared to Site report | Incorrect Test result | The issue is being handled with a PBI | Missing requirement
74 | Closed | Resolved | High | D4-HVC | 2023-02-21 | Defect | HVC Plant SOM | HVC-PL-53 | 658333 | UAT: HVC-PL-53: Maintenance Time (Hours) is not calculated properly. | Invalid result | Fixed | Missing requirement to test the Total for the required KPIs/Metrics
75 | Open | Resolved | Medium | D4 | 2023-02-27 | Defect |  |  | 659870 | UAT ¦ Totals are not showing correctly for % Online Time, Effective Asset Utilization, Maintenance Availability, Physical Availability and Mean time Between Downs (Hours) | Invalid result | The issue is resolved | Missing requirement to test the Total for the required KPIs/Metrics
76 | Open | Resolved | Medium | D4 | 2023-02-27 | Defect |  |  | 659871 | UAT ¦ Total are not showing correctly for Available Time, Calendar Time, Utilized Time and Production Time, Mean Down Time (Hours), Mean Time Between Down and Tonnes Processed | Invalid result | The issue is resolved | Missing requirement to test the Total for the required KPIs/Metrics
77 | Open | Created a PBI | Medium | D4 | 2023-02-27 | Defect |  |  | 659876 | UAT ¦ Auto Mill slicer for HVC SOM Metrics are not working correctly | Incorrect slicing | Created a PBI | Something changed after QA Functional Testing was completed, since testing completed 2 months before the code implemented in Prod
78 | Open | New | Medium | D5-HVC | 2023-02-27 | Defect | HVC-WO |  | 659937 | Comma Separators in Numbers not Present | Incorrect format | Need to retest after the cube merge | QA Defect
79 | Open | New | Medium | D5-HVC | 2023-02-27 | Defect | HVC-WO | HVC-WO-86 | 659949 | HVC WO /Compliance Rework - Duplication in Total Hours Reworked Fields | Duplicate measure | Need to retest after the cube merge | QA Defect
80 | Open | Created a PBI | Medium | D4-RDM | 2023-02-27 | Defect | RDM-Plant SOM | RDM-PL-47 | 659848 | UAT ¦ RDM ¦ RDM-PL-47:Total Number of Downs values are different in UAT and PROD | Invalid result | Created a PBI | QA discovered this issue during the smoke test. The requirement updated after QA Functional Testing was completed
81 | Closed | Resolved | Medium | D4 | 2023-02-27 | Defect |  |  | 659869 | Total Ore Adjusted Totals Incorrect | Invalid result | Issue resolved | Missing requirement to test the Total for the required KPIs/Metrics
82 | Closed | Cancelled | Medium | D4 | 2023-02-27 | Defect | FMS |  | 659974 | UAT: Asset Failure Count: The total on the Asset Failure Count is not adding up. | Invalid result | This is error in testing. | Testing error, not a defect
83 | Closed | Resolved | Critical | D4-RDM | 2023-03-01 | Defect | RDM-Plant SOM | RDM-PL-46 | 661842 | PRD: RDM Plant SOM: RDM-PL-46 : Daily Feed Rate When Running is showing in Production, it should be hidden | KPI/Metric should not be released in Prod | Completed QA testing | It is not a defect
84 | Open | New | Critical | D4 | 2023-03-02 | Defect | FMS |  | 661754 | PRD : Hot Fix: FMS: There are Blank Primary and Secondary Status Codes showing up for all the sites. | Invalid result | Hotfix item will be released on 2 March, 2023 with PBI 660764 | The issues were not present in QA and Pre-UAT.

## UAT Testing Results
Release | Site | KPI ID # | KPI Category | KPI Sub Category | KPI / Metric | Type | Source System | Test Script | Tester | Pass/Fail
R2 | RDO | RDO-WO/C-45 | Compliance | Compliance | Total Hours (Actual) - Mine | Metric | GenCID | RDO-WO C-45.MARS BM - UAT Test Script (Total Hours (Actual) - Mine)v2.docx | Robin Bailes | Pass
R2 | RDO | RDO-WO/C-86 | Compliance | Compliance | Total Hours (Actual) - Mill | Metric | GenCID | RDO-WO C-86.MARS BM - UAT Test Script (Total Hours (Actual) - Mill)v2.docx | Robin Bailes | Pass
R2 | RDO | RDO-WO/C-4 | Work Order | Work Order | # PMs Scheduled - Mill | Metric | GenCID | RDO-WO.C-4.MARS BM - UAT Test Script (# PMs Scheduled - Mill)v2.docx | Ntam Baharanyi | Pass
R2 | RDO | RDO-WO/C-6 | Work Order | Work Order | # Total Maintenance WO Completed - Mill | Metric | GenCID | RDO-WO.C-6.MARS BM - UAT Test Script (# Total Maintenance WO Completed - Mill)v2.docx | Ntam Baharanyi | Pass
R2 | RDO | RDO-WO/C-7 | Work Order | Work Order | # Scheduled Maintenance WO - Mill | Metric | GenCID | RDO-WO.C-7.MARS BM - UAT Test Script (# Scheduled Maintenance WO - Mill)v2.docx | Ntam Baharanyi | Pass
R2 | RDO | RDO-WO/C-13 | Work Order | Work Order | # PMs Scheduled - Mine | Metric | GenCID | RDO-WO.C-13.MARS BM - UAT Test Script (# PMs Scheduled - Mine)v2.docx | Ntam Baharanyi | Pass
R2 | RDO | RDO-WO/C-15 | Work Order | Work Order | # Total Maintenance WO Completed - Mine | Metric | GenCID | RDO-WO.C15.MARS BM - UAT Test Script (# Total Maintenance WO Completed - Mine)v2.docx | Ntam Baharanyi | Pass
R2 | RDO | RDO-WO/C-16 | Work Order | Work Order | # Scheduled Maintenance WO - Mine | Metric | GenCID | RDO-WO.C-16.MARS BM - UAT Test Script (# Scheduled Maintenance WO - Mine)v2.docx | Ntam Baharanyi | Pass
R2 | RDO | RDO-WO/C-44 | Compliance | Compliance | Total Distinct Work Order Count - Mine | Metric | GenCID | RDO-WO.C-44.MARS BM - UAT Test Script (Total Distinct Work Order Count - Mine)v2.docx | Robin Bailes | Pass
R2 | RDO | RDO-WO/C-62 | Compliance | Compliance | Total Work Order Count - Mine | Metric | GenCID | RDO-WO.C62.MARS BM - UAT Test Script (Total Work Order Count - Mine)v2.docx | Robin Bailes | Pass
R2 | RDO | RDO-WO/C-85 | Compliance | Compliance | Total Distinct Work Order Count - Mill | Metric | GenCID | RDO-WO.C-85.MARS BM - UAT Test Script (Total Distinct Work Order Count - Mill)v2.docx | Robin Bailes | Pass
R2 | RDO | RDO-WO/C-103 | Compliance | Compliance | Total Work Order Count - Mill | Metric | GenCID | RDO-WO.C-103.MARS BM - UAT Test Script (Total Work Order Count - Mill)v2.docx | Robin Bailes | Pass
R2 | HVC | HVC-WO-1 | Work Order | Work Order | Scheduled Maintenance WO Hours - Mill | Metric | JDE (Maintenance) | HVC-WO-1 MARS BM - UAT Test Script (Scheduled Maintenance WO Hours - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-103 | Compliance | Compliance | Total Work Order Count - Mill | Metric | JDE (Maintenance) | HVC-WO-103 MARS BM - UAT Test Script (Total Work Order Count - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-2 | Work Order | Work Order | Scheduled Maintenance WO Hours Completed - Mill | Metric | JDE (Maintenance) | HVC-WO-2 MARS BM - UAT Test Script (Scheduled Maintenance WO Hours Completed - Mill).docx | Paul Sundher | Testing
R2 | HVC | HVC-WO-3 | Work Order | Work Order | Non-scheduled Maintenance WO Hours Completed - Mill | Metric | JDE (Maintenance) | HVC-WO-3 MARS BM - UAT Test Script (Non-scheduled Maintenance WO Hours Completed - Mill).docx | Paul Sundher | Testing
R2 | HVC | HVC-WO-4 | Work Order | Work Order | # PMs Scheduled - Mill | Metric | JDE (Maintenance) | HVC-WO-4 MARS BM - UAT Test Script (# PMs Scheduled - Mill).docx | Paul Sundher | Testing
R2 | HVC | HVC-WO-5 | Work Order | Work Order | # PMs Completed as Scheduled - Mill | Metric | JDE (Maintenance) | HVC-WO-5 MARS BM - UAT Test Script (# PMs Completed as Scheduled - Mill).docx | Paul Sundher | Testing
R2 | HVC | HVC-WO-6 | Work Order | Work Order | # Total Maintenance WO Completed - Mill | Metric | JDE (Maintenance) | HVC-WO-6 MARS BM - UAT Test Script (# Total Maintenance WO Completed - Mill).docx | Paul Sundher | Testing
R2 | HVC | HVC-WO-7 | Work Order | Work Order | # Scheduled Maintenance WO - Mill | Metric | JDE (Maintenance) | HVC-WO-7 MARS BM - UAT Test Script (# Scheduled Maintenance WO - Mill).docx | Paul Sundher | Testing
R2 | HVC | HVC-WO-71 | Compliance | Compliance | Break-in Ratio (duration) - Mill | KPI | JDE (Maintenance) | HVC-WO-71 MARS BM - UAT Test Script (Break-in Ratio (duration) - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-76 | Compliance | Compliance | PM Schedule Compliance (By Duration) - Mill | KPI | JDE (Maintenance) | HVC-WO-76 MARS BM - UAT Test Script (PM Schedule Compliance (By Duration) - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-77 | Compliance | Compliance | PM Schedule Compliance (By Work Order Count) - Mill | KPI | JDE (Maintenance) | HVC-WO-77 MARS BM - UAT Test Script (PM Schedule Compliance (By Work Order Count) - Mill).docx | Paul Sundher | Testing
R2 | HVC | HVC-WO-78 | Compliance | Compliance | Schedule Compliance (By Duration) - Mill | KPI | JDE (Maintenance) | HVC-WO-78 MARS BM - UAT Test Script (Schedule Compliance (By Duration) - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-79 | Compliance | Compliance | Schedule Compliance (By Work Order Count) - Mill | KPI | JDE (Maintenance) | HVC-WO-79 MARS BM - UAT Test Script (Schedule Compliance (By Work Order Count) - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-8 | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | Metric | JDE (Maintenance) | HVC-WO-8 MARS BM - UAT Test Script (# Scheduled Maintenance WO Completed - Mill).docx | Paul Sundher | Testing
R2 | HVC | HVC-WO-80 | Compliance | Compliance | Schedule Load (Actual) - Mill | KPI | JDE (Maintenance) | HVC-WO-80 MARS BM - UAT Test Script (Schedule Load (Actual) - Mill).docx | Paul Sundher | Testing
R2 | HVC | HVC-WO-83 | Compliance | Compliance | Total Break-In Hours (Actual) - Mill | Metric | JDE (Maintenance) | HVC-WO-83 MARS BM - UAT Test Script (Total Break-In Hours (Actual) - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-85 | Compliance | Compliance | Total Distinct Work Order Count - Mill | Metric | JDE (Maintenance) | HVC-WO-85 MARS BM - UAT Test Script (Total Distinct Work Order Count - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-86 | Compliance | Compliance | Total Hours (Actual) - Mill | Metric | JDE (Maintenance) | HVC-WO-86 MARS BM - UAT Test Script (Total Hours (Actual) - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-88 | Compliance | Compliance | Total Hours (Scheduled) - Mill | Metric | JDE (Maintenance) | HVC-WO-88 MARS BM - UAT Test Script (Total Hours (Scheduled) - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-9 | Work Order | Work Order | # Non-scheduled Maintenance WO Completed - Mill | Metric | JDE (Maintenance) | HVC-WO-9 MARS BM - UAT Test Script (# Non-scheduled Maintenance WO Completed - Mill).docx | Paul Sundher | Testing
R2 | HVC | HVC-WO-97 | Compliance | Compliance | Total Non Break-In Hours (Actual) - Mill | Metric | JDE (Maintenance) | HVC-WO-97 MARS BM - UAT Test Script (Total Non Break-In Hours (Actual) - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-98 | Compliance | Compliance | Total Non Break-In PM Hours (Actual) - Mill | Metric | JDE (Maintenance) | HVC-WO-98 MARS BM - UAT Test Script (Total Non Break-In PM Hours (Actual) - Mill).docx | Paul Sundher | Pass
R2 | HVC | HVC-WO-99 | Compliance | Compliance | Total PM Hours (Scheduled) - Mill | Metric | JDE (Maintenance) | HVC-WO-99 MARS BM - UAT Test Script (Total PM Hours (Scheduled) - Mill).docx | Paul Sundher | Pass
R3 | CDA | CDA-PL-30 | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Metric | PIS | CDA-PL-30 MARS BM - UAT Test Script (Copper Tails Grade (Zinc Tails Grade)).docx | Miguel Vargas Romero | Pass
R3 | CDA | CDA-PL-31 | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Metric | PIS | CDA-PL-31 MARS BM - UAT Test Script (Copper Conc Produced (Zinc Conc Produced)).docx | Miguel Vargas Romero | Pass
R3 | CDA | CDA-PL-32 | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Metric | PIS | CDA-PL-32 MARS BM - UAT Test Script (Copper Contained in Cu Conc (Zinc Contained in Zinc Conc)).docx | Miguel Vargas Romero | Pass
R3 | CDA | CDA-PL-33 | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Metric | PIS | CDA-PL-33 MARS BM - UAT Test Script (Copper Conc Mo Grade Zinc Con Pb Grade).docx | Miguel Vargas Romero | Defer to Mario
R3 | CDA | CDA-PL-34 | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade | Metric | PIS | CDA-PL-34 MARS BM - UAT Test Script (Copper Conc Insol Grade Zinc Conc. Ag Grade).docx | Miguel Vargas Romero | Defer to Mario
R3 | CDA | CDA-PL-35 | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Metric | PIS | CDA-PL-35 MARS BM - UAT Test Script (Plant Yield (Adjusted)).docx | Miguel Vargas Romero | Testing
R3 | CDA | CDA-PL-38 | Plant | Plant Production Metrics | Total Metal (Adjusted) | Metric | PIS | CDA-PL-38 MARS BM - UAT Test Script (Total Metal (Adjusted)).docx | Miguel Vargas Romero | Testing
R3 | CDA | CDA-PL-40 | Plant | Plant Production Metrics | Total ore (Adjusted) | Metric | PIS | CDA-PL-40 MARS BM - UAT Test Script (Total ore (Adjusted)).docx | Miguel Vargas Romero | Testing
R3 | CDA | CDA-PL-44 | Plant | Plant Assay | Recovery % - Cu | KPI | PIS | CDA-PL-44 MARS BM - UAT Test Script (Recovery % - Cu).docx | Miguel Vargas Romero | Failed

## UAT Testing Schedule
Site | KPI ID # | KPI Macro Category | KPI Category | KPI Sub Category | KPI / Metric (ORG) | KPI / Metric As Built Name | Release | Type | Source System | Testing Order | Proposed Tester | Time | Date | Pre-UAT Passed | UAT Passed | Count of KPI IDS | Sumary Status | Summary Comment | Deployment/ Dpl Target | KPI Catlouge 12:37 2.22.2023 |  |  | D4 Target@ 12:47 2.22.2023
RDM | RDM-WO/C-62 | Compliance and Workorder | Compliance | Compliance | Total Work Order Count - Mine |  | R2 | Metric | GenCID | 1 | Robin Bailes | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
RDM | RDM-WO/C-103 | Compliance and Workorder | Compliance | Compliance | Total Work Order Count - Mill |  | R2 | Metric | GenCID | 1 | Robin Bailes | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
RDM | RDM-WO/C-45 | Compliance and Workorder | Compliance | Compliance | Total Hours (Actual) - Mine |  | R2 | Metric | GenCID | 1 | Robin Bailes | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
RDM | RDM-WO/C-86 | Compliance and Workorder | Compliance | Compliance | Total Hours (Actual) - Mill |  | R2 | Metric | GenCID | 1 | Robin Bailes | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
RDM | RDM-WO/C-44 | Compliance and Workorder | Compliance | Compliance | Total Distinct Work Order Count - Mine |  | R2 | Metric | GenCID | 1 | Robin Bailes | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
RDM | RDM-WO/C-85 | Compliance and Workorder | Compliance | Compliance | Total Distinct Work Order Count - Mill |  | R2 | Metric | GenCID | 1 | Robin Bailes | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
RDM | RDM-WO/C-15 | Compliance and Workorder | Work Order | Work Order | # Total Maintenance WO Completed - Mine |  | R2 | Metric | GenCID | 1 | Ntam Baharanyi | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
RDM | RDM-WO/C-6 | Compliance and Workorder | Work Order | Work Order | # Total Maintenance WO Completed - Mill |  | R2 | Metric | GenCID | 1 | Ntam Baharanyi | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
RDM | RDM-WO/C-16 | Compliance and Workorder | Work Order | Work Order | # Scheduled Maintenance WO - Mine |  | R2 | Metric | GenCID | 1 | Ntam Baharanyi | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1 | 9
RDM | RDM-WO/C-7 | Compliance and Workorder | Work Order | Work Order | # Scheduled Maintenance WO - Mill |  | R2 | Metric | GenCID | 1 | Ntam Baharanyi | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
RDM | RDM-WO/C-13 | Compliance and Workorder | Work Order | Work Order | # PMs Scheduled - Mine |  | R2 | Metric | GenCID | 1 | Ntam Baharanyi | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
RDM | RDM-WO/C-4 | Compliance and Workorder | Work Order | Work Order | # PMs Scheduled - Mill |  | R2 | Metric | GenCID | 1 | Ntam Baharanyi | 0.25 | Complete- Nov 7 & 8th (9th Added) | Yes | Yes | 1 | Deployed |  | D1
HVC | HVC-WO-103 | Compliance and Workorder | Compliance | Compliance | Total Work Order Count - Mill |  | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-99 | Compliance and Workorder | Compliance | Compliance | Total PM Hours (Scheduled) - Mill |  | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
CDA | CDA-PL-40 | Plant | Plant | Plant Production Metrics | Total ore (Adjusted) |  | R3 | Metric | PIS | 3 | Miguel Vargas Romero | 0.25 | Complete- Dec 1 & 9 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-98 | Compliance and Workorder | Compliance | Compliance | Total Non Break-In PM Hours (Actual) - Mill |  | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-97 | Compliance and Workorder | Compliance | Compliance | Total Non Break-In Hours (Actual) - Mill |  | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
CDA | CDA-PL-38 | Plant | Plant | Plant Production Metrics | Total Metal (Adjusted) |  | R3 | Metric | PIS | 3 | Miguel Vargas Romero | 0.25 | Complete- Dec 1 & 8 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-88 | Compliance and Workorder | Compliance | Compliance | Total Hours (Scheduled) - Mill |  | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-86 | Compliance and Workorder | Compliance | Compliance | Total Hours (Actual) - Mill |  | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-85 | Compliance and Workorder | Compliance | Compliance | Total Distinct Work Order Count - Mill |  | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-83 | Compliance and Workorder | Compliance | Compliance | Total Break-In Hours (Actual) - Mill |  | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-1 | Compliance and Workorder | Work Order | Work Order | Scheduled Maintenance WO Hours - Mill |  | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-79 | Compliance and Workorder | Compliance | Compliance | Schedule Compliance (By Work Order Count) - Mill |  | R2 | KPI | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-78 | Compliance and Workorder | Compliance | Compliance | Schedule Compliance (By Duration) - Mill |  | R2 | KPI | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-76 | Compliance and Workorder | Compliance | Compliance | PM Schedule Compliance (By Duration) - Mill |  | R2 | KPI | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | Yes | 1 | Deployed |  | D2
CDA | CDA-PL-35 | Plant | Plant | Plant Production Metrics | Plant Yield (Adjusted) |  | R3 | Metric | PIS | 3 | Miguel Vargas Romero | 0.25 | Complete- Dec 1 & 7 | Yes | Yes | 1 | Deployed |  | D2
CDA | CDA-PL-30 | Plant | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) |  | R3 | Metric | PIS | 3 | Miguel Vargas Romero/Mario | 0.25 | Complete- Dec 1 & 2 | Yes | Yes | 1 | Deployed |  | D2
CDA | CDA-PL-32 | Plant | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) |  | R3 | Metric | PIS | 3 | Miguel Vargas Romero | 0.25 | Complete- Dec 1 & 4 | Yes | Yes | 1 | Deployed |  | D2
CDA | CDA-PL-31 | Plant | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) |  | R3 | Metric | PIS | 3 | Miguel Vargas Romero | 0.25 | Complete- Dec 1 & 3 | Yes | Yes | 1 | Deployed |  | D2
CDA | CDA-PL-33 | Plant | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade |  | R3 | Metric | PIS | 3 | Miguel Vargas Romero | 0.25 | Complete- Dec 1 & 5 | Yes | Yes | 1 | Deployed |  | D2
CDA | CDA-PL-34 | Plant | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade |  | R3 | Metric | PIS | 3 | Miguel Vargas Romero | 0.25 | Complete- Dec 1 & 6 | Yes | Yes | 1 | Deployed |  | D2
HVC | HVC-WO-71 | Compliance and Workorder | Compliance | Compliance | Break-in Ratio (duration) - Mill |  | R2 | KPI | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 22 | Yes | Yes | 1 | Deployed |  | D2
RDM | RDM-ME-22 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Use of Availability (Actual) |  | R1 | KPI | Cloud IO <35 days and >35 days | 5 | TBD | 0.25 | TBD | No | No | 1 | Deployed |  | D3 | 3
RDM | RDM-PL-26 | Plant | Plant | Plant Downtime | Total Stream Downtime (Hours) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-41 | Plant | Plant | Plant Production Metrics | Total ore (Unadjusted) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-40 | Plant | Plant | Plant Production Metrics | Total ore (Adjusted) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-39b | Plant | Plant | Plant Production Metrics | Total Metal Lead (Unadjusted) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3 | 8
RDM | RDM-PL-38b | Plant | Plant | Plant Production Metrics | Total Metal Lead (Adjusted) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-39 | Plant | Plant | Plant Production Metrics | Total Metal (Unadjusted) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-38 | Plant | Plant | Plant Production Metrics | Total Metal (Adjusted) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-15 | Plant | Plant | Plant Standard Operating Metrics | Tonnes Processed (Total Milled in SMT) | Tonnes Processed | R3 | Metric | GenCID | 4 | Randy Lewelellen | 0.25 | UAT Dec | No | No | 1 | Deployed |  | D3
RDM | RDM-PL-44a | Plant | Plant | Plant Assay | Recovery % - Zn |  | R3 | KPI | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-44b | Plant | Plant | Plant Assay | Recovery % - Pb |  | R3 | KPI | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3 | 7
RDM | RDM-PL-36 | Plant | Plant | Plant Production Metrics | Plant Yield (Unadjusted) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-35 | Plant | Plant | Plant Production Metrics | Plant Yield (Adjusted) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-5b | Plant | Plant | Plant Standard Operating Metrics | Plant Production Rate |  | R3 | KPI | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-21 | Plant | Plant | Plant Standard Operating Metrics | Plant Feed Rate |  | R3 | KPI | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3 | 11
RDM | RDM-PL-6 | Plant | Plant | Plant Standard Operating Metrics | Physical Availability |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-ME-21 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Operating Efficiency (Actual) |  | R1 | Metric | Cloud IO <35 days and >35 days | 5 | TBD | 0.25 | TBD | No | No | 1 | Deployed |  | D3
RDM | RDM-PL-14 | Plant | Plant | Plant Standard Operating Metrics | Number of Maintenance Events |  | R3 | Metric | GenCID | 4 | Randy Lewelellen | 0.25 | UAT Dec | No | No | 1 | Critical Issue/Bug-PreUAT | See Arjun's Comments | D3
RDM | RDM-ME-20 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mobile Availability (Actual) |  | R1 | Metric | Cloud IO <35 days and >35 days | 5 | TBD | 0.25 | TBD | No | No | 1 | Deployed |  | D3
RDM | RDM-ME-19 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time To Repair (Hours) |  | R1 | KPI | Cloud IO <35 days and >35 days | 5 | TBD | 0.25 | TBD | No | No | 1 | Deployed |  | D3
RDM | RDM-ME-18 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Failure (Hours) |  | R1 | KPI | Cloud IO <35 days and >35 days | 5 | TBD | 0.25 | TBD | No | No | 1 | Deployed |  | D3
RDM | RDM-PL-4 | Plant | Plant | Plant Standard Operating Metrics | Mean Time Between Downs (Hours) |  | R3 | KPI | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-ME-17 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Down (Hours) |  | R1 | KPI | Cloud IO <35 days and >35 days | 5 | TBD | 0.25 | TBD | No | No | 1 | Deployed |  | D3
RDM | RDM-ME-16 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Failure Time (Hours) |  | R1 | KPI | Cloud IO <35 days and >35 days | 5 | TBD | 0.25 | TBD | No | No | 1 | Deployed |  | D3
RDM | RDM-PL-3 | Plant | Plant | Plant Standard Operating Metrics | Mean Down Time (Hours) |  | R3 | KPI | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-ME-15 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Down Time (Hours) |  | R1 | KPI | Cloud IO <35 days and >35 days | 5 | TBD | 0.25 | TBD | Yes | No | 1 | Deployed |  | D3
RDM | RDM-ME-14 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Availability (Actual) |  | R1 | KPI | Cloud IO <35 days and >35 days | 5 | TBD | 0.25 | TBD | Yes | No | 1 | Deployed |  | D3
RDM | RDM-PL-2 | Plant | Plant | Plant Standard Operating Metrics | Maintenance Availability |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-1 | Plant | Plant | Plant Standard Operating Metrics | Effective Asset Utilization |  | R3 | KPI | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-12 | Plant | Plant | Plant Standard Operating Metrics | Daily Production Rate When Running |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-30 | Plant | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-32 | Plant | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-31 | Plant | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-33 | Plant | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Zinc Con Pb Grade % | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-34 | Plant | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-13 | Plant | Plant | Plant Standard Operating Metrics | Best Daily Production Rate |  | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
RDM | RDM-PL-5 | Plant | Plant | Plant Standard Operating Metrics | % Capacity |  | R3 | KPI | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | Yes | 1 | Deployed |  | D3
HVC | HVC-PL-44 | Plant | Plant | Plant Assay | Recovery % - Cu | Recovery % - Cu | R3 | KPI | PARCview | 4 | Frank Laroche | 0.25 | UAT Feb 6 | Yes | Yes | 1 | UAT Passed |  | D4 | 1 | 1 |  | 1
HVC | HVC-PL-58 | Plant | Plant SOM | Standard Time Definitions | Utilized Time (Hours) | Utilized Time (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
CDA | CDA-ME-22 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Use of Availability (Actual) | FMS Use of Availability (Actual) | R1 | KPI | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-22 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Use of Availability (Actual) | FMS Use of Availability (Actual) | R5 | KPI | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 | 4 |  | 1
HVC | HVC-PL-40 | Plant | Plant | Plant Production Metrics | Total ore (Adjusted) | Total ore (Adjusted) | R3 | Metric | PARCview | 4 | Frank Laroche | 0.25 | UAT Feb 6 | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-47 | Plant | Plant SOM | Plant Standard Operating Metrics | Total Number of Downs | Total Number of Downs | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-38 | Plant | Plant | Plant Production Metrics | Total Metal (Adjusted) | Total Metal - Copper (Adjusted) | R3 | Metric | PARCview | 4 | Frank Laroche | 0.25 | UAT Feb 6 | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-57 | Plant | Plant SOM | Standard Time Definitions | Standby Time (Hours) | Standby Time (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-56 | Plant | Plant SOM | Standard Time Definitions | Production Time (Hours) | Production Time (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-35 | Plant | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Plant Yield - Copper (Adjusted) | R3 | Metric | PARCview | 4 | Frank Laroche | 0.25 | UAT Feb 6 | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-23 | Plant Standard Operating Metrics | Plant | Plant SOM | Plant Production Rate | % Capacity Plant Production Rate Plant Prodcution Rate | R5 | SOM | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-21 | Plant Standard Operating Metrics | Plant | Plant SOM | Plant Feed Rate | Plant Feed Rate | R5 | SOM | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-6 | Plant Standard Operating Metrics | Plant | Plant SOM | Physical Availability | Physical Availability | R5 | SOM | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1
CDA | CDA-ME-21 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Operating Efficiency (Actual) | FMS Operating Efficiency (Actual) | R1 | Metric | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-21 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Operating Efficiency (Actual) | FMS Operating Efficiency (Actual) | R5 | KPI | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Critical Issue/Bug-UAT |  | D4 | 1 |  |  | 1 | 9
HVC | HVC-PL-55 | Plant | Plant SOM | Standard Time Definitions | Operating Delays (Hours) | Operating Delays (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-14 | Plant Standard Operating Metrics | Plant | Plant SOM | Number of Maintenance Events |  | R5 | SOM | PARCview | 7 | TBD | 0.25 | TBD | No | No | 1 | In Pre-UAT | Pre-UAT Arjun | D4 | 1
CDA | CDA-ME-20 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mobile Availability (Actual) | FMS Mobile Availability (Actual) | R1 | Metric | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-20 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mobile Availability (Actual) | FMS Mobile Availability (Actual) | R5 | KPI | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Critical Issue/Bug-UAT |  | D4 | 1 |  |  | 1 | 3
CDA | CDA-ME-19 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time To Repair (Hours) | FMS Mean Time To Repair (Hours) | R1 | KPI | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-19 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time To Repair (Hours) | FMS Mean Time To Repair (Hours) | R5 | KPI | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Critical Issue/Bug-UAT |  | D4 | 1 |  |  | 1
CDA | CDA-ME-18 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Failure (Hours) | FMS Mean Time Between Failure (Hours) | R1 | KPI | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-18 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Failure (Hours) | FMS Mean Time Between Failure (Hours) | R5 | KPI | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-4 | Plant Standard Operating Metrics | Plant | Plant SOM | Mean Time Between Downs (Hours) | Mean Time Between Downs (Hours) | R5 | SOM | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
CDA | CDA-ME-17 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Down (Hours) | FMS Mean Time Between Down (Hours) | R1 | KPI | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-17 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Down (Hours) | FMS Mean Time Between Down (Hours) | R5 | KPI | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
CDA | CDA-ME-16 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Failure Time (Hours) | FMS Mean Failure Time (Hours) | R1 | KPI | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1 | 8
HVC | HVC-ME-16 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Failure Time (Hours) | FMS Mean Failure Time (Hours) | R5 | KPI | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
CDA | CDA-ME-15 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Down Time (Hours) | FMS Mean Down Time (Hours) | R1 | KPI | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-3 | Plant Standard Operating Metrics | Plant | Plant SOM | Mean Down Time (Hours) | Mean Down Time (Hours) | R5 | SOM | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-15 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Down Time (Hours) | FMS Mean Down Time (Hours) | R5 | KPI | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-54 | Plant | Plant SOM | Standard Time Definitions | Major Maintenance Shutdown (Hours) | Major Maintenance Shutdown (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed | May be reversed labeling with HVCPL52 | D4 | 1 |  |  | 1
HVC | HVC-PL-53 | Plant | Plant SOM | Standard Time Definitions | Maintenance Time (Hours) | Maintenance Time (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-52 | Plant | Plant SOM | Standard Time Definitions | Maintenance Scheduled (Hours) | Maintenance Scheduled (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed | May be reversed labeling with HVCPL54 | D4 | 1 |  |  | 1
HVC | HVC-PL-51 | Plant | Plant SOM | Standard Time Definitions | Maintenance Non Scheduled (Hours) | Maintenance Non Scheduled (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
CDA | CDA-ME-14 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Availability (Actual) | FMS Maintenance Availability (Actual) | R1 | KPI | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed | Noted Issue: Site Metric differ from SOM | D4 | 1 |  |  | 1
HVC | HVC-ME-14 | Fleet | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Availability (Actual) | FMS Maintenance Availability (Actual) | R5 | KPI | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-2 | Plant Standard Operating Metrics | Plant | Plant SOM | Maintenance Availability | Maintenance Availability | R5 | SOM | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1
CDA | CDA-ME-49 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Utilized Time (Actual) | FMS Total Utilized Time (Actual) | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 | 21 |  | 1
HVC | HVC-ME-49 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Utilized Time (Actual) | FMS Total Utilized Time (Actual) | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1
CDA | CDA-ME-48 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Standby Hours (Actual) | FMS Total Standby Hours (Actual) | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-48 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Standby Hours (Actual) | FMS Total Standby Hours (Actual) | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1
CDA | CDA-ME-47 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Production Time (Hours) (Actual) | FMS Total Production Time (Hours) (Actual) | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-47 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Production Time (Hours) (Actual) | FMS Total Production Time (Hours) (Actual) | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1
CDA | CDA-ME-46 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Operational Delay Hours (Actual) | FMS Total Operational Delay Hours (Actual) | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-46 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Operational Delay Hours (Actual) | FMS Total Operational Delay Hours (Actual) | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1
CDA | CDA-ME-45 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Hours (Actual) | FMS Total Maintenance Hours (Actual) | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-45 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Hours (Actual) | FMS Total Maintenance Hours (Actual) | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1 | 21
CDA | CDA-ME-44 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Delay Hours (Actual) | FMS Total Maintenance Delay Hours (Actual) | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-44 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Delay Hours (Actual) | FMS Total Maintenance Delay Hours (Actual) | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1
CDA | CDA-ME-43 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Excluded Calendar Hours (Actual) | FMS Total Excluded Calendar Hours (Actual) | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-43 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Excluded Calendar Hours (Actual) | FMS Total Excluded Calendar Hours (Actual) | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1
CDA | CDA-ME-42 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Available Time (Actual) | FMS Total Available Time (Actual) | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-42 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Available Time (Actual) | FMS Total Available Time (Actual) | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1
CDA | CDA-ME-41 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Active Maintenance Hours (Actual) | FMS Total Active Maintenance Hours (Actual) | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-41 | Fleet | Mobile Equipment Avail. | Mobile SOM | FMS Total Active Maintenance Hours (Actual) | FMS Total Active Maintenance Hours (Actual) | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Failed-Dep |  | D4 | 1 |  |  | 1
HVC | HVC-PL-50 | Plant | Plant SOM | Standard Time Definitions | Excluded Calendar Time (Hours) | Excluded Calendar Time (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-1 | Plant Standard Operating Metrics | Plant | Plant SOM | Effective Asset Utilization | Effective Asset Utilization | R5 | SOM | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-12 | Plant | Plant SOM | Plant Standard Operating Metrics | Daily Production Rate When Running | Daily Production Rate When Running | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-46 | Plant | Plant SOM | Plant Standard Operating Metrics | Daily Feed Rate When Running | Daily Feed Rate When Running | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-30 | Plant | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Copper Tails Grade % | R3 | Metric | PARCview | 4 | Frank Laroche | 0.25 | UAT Feb 6 | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-32 | Plant | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Copper Contained in Cu Conc % | R3 | Metric | PARCview | 4 | Frank Laroche | 0.25 | UAT Feb 6 | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-31 | Plant | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Copper Conc Produced | R3 | Metric | PARCview | 4 | Frank Laroche | 0.25 | UAT Feb 6 | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-33 | Plant | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Copper Conc Mo GradeCopper Conc Mo Grade % | R4 | Metric | PARCview | 5 | Frank Laroche | 1.25 | UAT Feb 6 | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-49 | Plant | Plant SOM | Standard Time Definitions | Calendar Time (Hours) | Calendar Time (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-48 | Plant | Plant SOM | Standard Time Definitions | Available Time (Hours) | Available Time (Hours) | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
CDA | CDA-ME-40 | Fleet | Mobile Equipment Avail. | Mobile SOM | Asset Failure Count | Asset Failure Count | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed | Noted Issue: Substatus code not being used at Site | D4 | 1 |  |  | 1
HVC | HVC-ME-40 | Fleet | Mobile Equipment Avail. | Mobile SOM | Asset Failure Count | Asset Failure Count | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
CDA | CDA-ME-39 | Fleet | Mobile Equipment Avail. | Mobile SOM | Asset Event Count | Asset Event Count | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-39 | Fleet | Mobile Equipment Avail. | Mobile SOM | Asset Event Count | Asset Event Count | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
CDA | CDA-ME-38 | Fleet | Mobile Equipment Avail. | Mobile SOM | Asset Down Count | Asset Down Count | R1 |  | Cloud IO <35 days and >35 days | 6 | Pablo Galleguillos Astorga | 0.25 | Feb 9th (To Feb 15) | Yes | Yes | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-ME-38 | Fleet | Mobile Equipment Avail. | Mobile SOM | Asset Down Count | Asset Down Count | R5 | Metric | Minestar Wenco | 9 | TBD | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
RDM | RDM-PL-7 | Plant | Plant | Plant Standard Operating Metrics | % Online Time | % Online Time | R3 | KPI | GenCID | 4 | Randy Lewelellen | 0.25 | UAT Dec | No | No | 1 | UAT Passed | Note: Works only for SAG | D4 | 1 |  |  | 1
HVC | HVC-PL-7 | Plant | Plant SOM | Plant Standard Operating Metrics | % Online Time | % Online Time | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed |  | D4 | 1 |  |  | 1
HVC | HVC-PL-15 |  |  |  |  | Tonnes Proccessed | R5 | Metric | PARCview |  | Bruno/Frank | 1.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | UAT Passed | Added to D4. Previously Missed | D4 | 1 | 29 |  | 1
RDM | RDM-FI-4 | Finance | Finance | Finance General Ledger | Total Costs (Actual) | Total Costs (Actual) | R5 | Metric | Gencid | 8 | Robin Bailes | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Move to D5-Critical Issue/Bug-UAT | Link to Many table. Inflated results | D4 D5 | 1 |  |  | 0
RDM | RDM-FI-3 | Finance | Finance | Finance General Ledger | Site Cash Production Cost (Actual) | Site Cash Production Cost (Actual) | R5 | Metric | Gencid | 8 | Robin Bailes | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Move to D5-Critical Issue/Bug-UAT | Link to Many table. Inflated results | D4 D5 | 1 |  |  | 0 | 27
HVC | HVC-WO-2 | Compliance and Workorder | Work Order | Work Order | Scheduled Maintenance WO Hours Completed - Mill | Scheduled Maintenance WO Hours Completed | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
CDA | CDA-PL-44 | Plant | Plant | Plant Assay | Recovery % - Cu | Recovery % - Cu | R3 | KPI | PIS | 3 | Miguel Vargas Romero | 0.25 | Complete- Dec 1 & 10 | Yes | No | 1 | Move to D5-Critical Issue/Bug-UAT | Formula Issue. W Gerry | D4 D5 | 1 | 5 |  | 0
HVC | HVC-WO-77 | Compliance and Workorder | Compliance | Compliance | PM Schedule Compliance (By Work Order Count) - Mill | PM Schedule Compliance (By Work Order Count) | R2 | KPI | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
RDM | RDM-PL-5b | Plant | Plant | Plant Standard Operating Metrics | Plant Production Rate % Capacity Plant Production Rate | % Capacity Plant Production Rate | R3 | KPI | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | TBC | Yes | See Note | 1 | Move to D5-Critical Issue/Bug-UAT | Under review. Not aligned with SOM Intent. | D4 D5 | 1
RDM | RDM-PL-9 | Plant Finance | Plant | Plant Standard Operating Metrics | Plant Department Site Cash Production Cost Per Operating Hours (Actual) | Plant Department Site Cash Production Cost Per Monthly Plant Operating Hours (Actual) | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | See Note | 1 | Move to D5-Critical Issue/Bug-UAT | UAT passed for 2022 and prior.Problem W 2023. W Kirk | D4 D5 | 1
RDM | RDM-FI-2 | Finance | Finance | Finance Planning | Plant Department Site Cash Production Cost (Actual) | Plant Department Site Cash Production Cost (Actual) | R5 | Metric | Gencid | 8 | Robin Bailes | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Move to D5-Critical Issue/Bug-UAT | Link to Many table. Inflated results | D4 D5 | 1 |  |  | 0
HVC | HVC-WO-3 | Compliance and Workorder | Work Order | Work Order | Non-scheduled Maintenance WO Hours Completed - Mill | Non-Scheduled Maintenance WO Hours Completed | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
RDM | RDM-FI-20 | Finance | Finance | Finance Planning | Maintenance Department Site Cash Production Cost (Actual) | Maintenance Department Site Cash Production Cost (Actual) | R5 | Metric | Gencid | 8 | Robin Bailes | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Move to D5-Critical Issue/Bug-UAT | Link to Many table. Inflated results | D4 D5 | 1 |  |  | 0
HVC | HVC-WO-6 | Compliance and Workorder | Work Order | Work Order | # Total Maintenance WO Completed - Mill | # Total Maintenance WO Completed | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
HVC | HVC-WO-8 | Compliance and Workorder | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | # Scheduled Maintenance WO Completed | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 | 9 |  | 0
HVC | HVC-WO-7 | Compliance and Workorder | Work Order | Work Order | # Scheduled Maintenance WO - Mill | # Scheduled Maintenance WO | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
HVC | HVC-WO-4 | Compliance and Workorder | Work Order | Work Order | # PMs Scheduled - Mill | # PMs Scheduled | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
HVC | HVC-WO-5 | Compliance and Workorder | Work Order | Work Order | # PMs Completed as Scheduled - Mill | # PMs Completed as Scheduled | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
HVC | HVC-WO-9 | Compliance and Workorder | Work Order | Work Order | # Non-scheduled Maintenance WO Completed - Mill | # Non-Scheduled Maintenance WO Completed | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
HVC | HVC-PL-13 | Plant | Plant SOM | Plant Standard Operating Metrics | Best Daily Production Rate | Best Daily Production Rate | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to D5-Critical Issue/Bug-UAT | Under review. Not aligned with SOM Intent. | D4 D5' | 0 |  |  | 0
HVC | HVC-PL-45 | Plant | Plant SOM | Plant Standard Operating Metrics | Best Daily Feed Rate | Best Daily Feed Rate | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to D5-Critical Issue/Bug-UAT | Under review. Not aligned with SOM Intent. | D4 D5' | 0 |  |  | 0
HVC | HVC-PL-23 HVC-PL-5B | Plant | Plant SOM | Plant Standard Operating Metrics | % Capacity Plant Production Rate | % Capacity Plant Production Rate | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to D5-Critical Issue/Bug-UAT | Under review. Not aligned with SOM Intent. | D4 D5' | 0 |  |  | 0
HVC | HVC-PL-5 | Plant | Plant SOM | Plant Standard Operating Metrics | % Capacity Plant Feed Rate | % Capacity Plant Feed Rate | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to D5-Critical Issue/Bug-UAT | Under review. Not aligned with SOM Intent. | D4 D5' | 0 |  |  | 0
HVC | HVC-PL-17 | Plant Standard Operating Metrics | Plant | Plant SOM | Plant Maintenance Internal Labor Hours | Plant Maintenance Internal Labor Hours | R5 | Metric | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to Backlog | Jacob. Deffer | Move to Backlog | 0
HVC | HVC-PL-22 | Plant Standard Operating Metrics | Plant | Plant SOM | Plant Labor Factor (Internal Labor Factor) | Plant Labor Factor (Internal Labor Factor) | R5 | KPI | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to Backlog | Jacob. Deffer | Move to Backlog | 0
RDM | RDM-PL-27 | Plant | Plant | Plant Downtime | Total Stream Event Count | Total Stream Event Count | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | No | 1 | Recommend De-scope | Source Data Issue. Genid stores combined | Recommend De-scope | 1 |  |  |  | 0
HVC | HVC-WO-80 | Compliance and Workorder | Compliance | Compliance | Schedule Load (Actual) - Mill |  | R2 | KPI | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | No | 1 | Deffered | Name issue | TBD | 0 |  | Confirm Out of scope (with Don)
HVC | HVC-PL-34 | Plant | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade |  | R3 | Metric | PARCview | 4 | Frank Laroche | 0.25 | Complete | No | No | 1 | Critical Issue/Bug-PreUAT | Deffered Source Issue-HVC is updating their tags so once complete this can be retested (Two week outage with the site) Update: Postponed unitl site Changes Source | TBD | 0
|  | Deffered/Descope | 7 |  | Total | 0
|  | Critical Issue/Bug-UAT | 3 |  | Total | 0
|  | UAT Passed/Critical Issue-Dep | 11 |  | Recommend De-scope | 1 | [17 empty] | 0
|  | Summary Table D4 (KPI Catlouge Aligned) |  |  | Moved to D5-Critical Issue/Bug-UAT | 4 | [17 empty] | 68
|  | Move to D5-In UAT | 9 |  | Move to D5-Critical Issue/Bug-UAT | 7
|  | Deployed | 0 |  | Move to Backlog | 2
|  | UAT Passed | 54 |  | Deffered/Descoped
[5 empty] | Changed in KPI Catalouge | [10 empty] | 23 |  |  |  |  | #REF!
D3 Documentation above fix required-Add supporting Metric and change down Events metric
D4 | Updated | 2.13.2023
-RDM RT Duet |  | 9 | Being Built-Needs Testing of Source; Business Validation, QA | [19 empty] | 0
|  | Critical Issue/Bug-UAT | # of Metrics | # metric Impacted (Cum) | [18 empty] | 0
|  | D4 Critical Issue/Bugs- Summary | [18 empty] | 0 |  | 0
|  | HVC FMS | 3 | 17 | [18 empty] | 0
|  | HVC Plant SOM | 2 | 6 | [18 empty] | 0
|  | Pre-UAT Passed | 0
|  | In Pre-UAT | 1
|  | Critical Issue/Bug-Pre UAT | 0
|  | In QA | 0
|  | Total | 6
|  | Total | 6 | 0
RDM | RDM-PL-46 | Plant | Plant Standard Operating Metrics | Daily Feed Rate When Running | Metric | Gencid | D4
D5 March
RDM | RDM-PL-26-RT | Plant | Plant Downtime |  | Total Stream Downtime (Hours) | Gencid/Rt Duet-Contous (3 day vs. 1) |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-27-RT | Plant | Plant Downtime |  | Total Stream Event Count | Gencid/Rt Duet (Gencid Each Day a down 3 event/ 1 Event) |  | Metric | RT-DUET* | 1 | [5 empty] | 1
RDM | RDM-PL-51-RT | Plant | Plant SOM |  | Maintenance Non Scheduled (Hours) |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-52-RT | Plant | Plant SOM |  | Maintenance Scheduled (Hours) |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-53-RT | Plant | Plant SOM |  | Maintenance Time (Hours) |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-54-RT | Plant | Plant SOM |  | Major Maintenance Shutdown (Hours) |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-55-RT | Plant | Plant SOM |  | Operating Delays (Hours) |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-57-RT | Plant | Plant SOM |  | Standby Time (Hours) |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-47-RT | Plant | Plant SOM |  | Total Number of Downs | Gencid/Rt Duet |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-7-RT | Plant | Plant SOM |  | % Online Time |  |  | KPI | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-3-RT | Plant | Plant SOM |  | Mean Down Time (Hours) | Gencid/Rt Duet |  | KPI | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-4-RT | Plant | Plant SOM |  | Mean Time Between Downs (Hours) | Gencid/Rt Duet |  | KPI | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-21-RT | Plant | Plant SOM |  | Plant Feed Rate |  |  | KPI | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-23-RT | Plant | Plant SOM |  | Plant Production Rate |  |  | KPI | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-1-RT | Plant | Plant SOM |  | Effective Asset Utilization |  |  | KPI | RT-DUET | 1 | [5 empty] | 0
RDM | RDM-PL-5b-RT | Plant | Plant SOM |  | % Capacity Plant Production Rate |  |  | KPI | RT-DUET | 0 | [5 empty] | 0 |  | 1 Under review for Alignment with SOM
RDM | RDM-PL-5-RT | Plant | Plant SOM |  | % Capacity Plant Feed Rate |  |  | KPI | RT-DUET | 0 | [5 empty] | 0 |  | 1 Under review for Alignment with SOM
RDM | RDM-PL-13-RT | Plant | Plant SOM |  | Best Daily Production Rate |  |  | Metric | RT-DUET | 0 | [5 empty] | 1
RDM | RDM-PL-48-RT | Plant | Plant SOM |  | Available Time (Hours) |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-2-RT | Plant | Plant SOM |  | Maintenance Availability |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-46-RT | Plant | Plant SOM |  | Daily Feed Rate When Running |  |  | Metric | RT-DUET* | 1 | [5 empty] | 1
RDM | RDM-PL-56-RT | Plant | Plant SOM |  | Production Time (Hours) |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-6-RT | Plant | Plant SOM |  | Physical Availability |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-58-RT | Plant | Plant SOM |  | Utilized Time (Hours) |  |  | Metric | RT-DUET | 1 | [5 empty] | 1
RDM | RDM-PL-12-RT | Plant | Plant SOM |  | Daily Production Rate When Running |  |  | Metric | RT-DUET | 1 | [5 empty] | 1 |  | 1 Under review for Alignment with SOM
RDM | RDM-PL-45-RT | Plant | Plant SOM |  | Best Daily Feed Rate |  |  | Metric | RT-DUET | 0 | 22 |  |  |  |  | 0 |  | 1 Under review for Alignment with SOM |  |  | 22
HVC | HVC-WO-2 | Compliance and Workorder | Work Order | Work Order | Scheduled Maintenance WO Hours Completed - Mill | Scheduled Maintenance WO Hours Completed | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 0 |  |  |  | Pulled ones from Oriaze #1 Mar 3. Note not approved.
HVC | HVC-WO-3 | Compliance and Workorder | Work Order | Work Order | Non-scheduled Maintenance WO Hours Completed - Mill | Non-Scheduled Maintenance WO Hours Completed | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 0 |  |  |  | Pulled ones from Oriaze #1 Mar 3. Note not approved.
HVC | HVC-WO-5 | Compliance and Workorder | Work Order | Work Order | # PMs Completed as Scheduled - Mill | # PMs Completed as Scheduled | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1
HVC | HVC-WO-4 | Compliance and Workorder | Work Order | Work Order | # PMs Scheduled - Mill | # PMs Scheduled | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
HVC | HVC-WO-6 | Compliance and Workorder | Work Order | Work Order | # Total Maintenance WO Completed - Mill | # Total Maintenance WO Completed | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
HVC | HVC-WO-7 | Compliance and Workorder | Work Order | Work Order | # Scheduled Maintenance WO - Mill | # Scheduled Maintenance WO | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
HVC | HVC-WO-8 | Compliance and Workorder | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | # Scheduled Maintenance WO Completed | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 |  |  | 0
HVC | HVC-WO-9 | Compliance and Workorder | Work Order | Work Order | # Non-scheduled Maintenance WO Completed - Mill | # Non-Scheduled Maintenance WO Completed | R2 | Metric | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1
HVC | HVC-WO-77 | Compliance and Workorder | Compliance | Compliance | PM Schedule Compliance (By Work Order Count) - Mill | PM Schedule Compliance (By Work Order Count) | R2 | KPI | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | UAT Nov 22 & Nov 23 | Yes | No | 1 | Move to D5-In UAT | Arjun Working on with Jodie | D4 D5 | 1 | 7 |  |  | Change
RDM | RDM-PL-9 | Plant Finance | Plant | Plant Standard Operating Metrics | Plant Department Site Cash Production Cost Per Operating Hours (Actual) | Plant Department Site Cash Production Cost Per Monthly Plant Operating Hours (Actual) | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | See Note | 1 | Move to D5-Critical Issue/Bug-UAT | UAT passed for 2022 and prior.Problem W 2023. W Kirk | D4 D5 | 1
RDM | RDM-FI-2 | Finance | Finance | Finance Planning | Plant Department Site Cash Production Cost (Actual) | Plant Department Site Cash Production Cost (Actual) | R5 | Metric | Gencid | 8 | Robin Bailes | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Move to D5-Critical Issue/Bug-UAT | Link to Many table. Inflated results | D4 D5 | 1
RDM | RDM-FI-20 | Finance | Finance | Finance Planning | Maintenance Department Site Cash Production Cost (Actual) | Maintenance Department Site Cash Production Cost (Actual) | R5 | Metric | Gencid | 8 | Robin Bailes | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Move to D5-Critical Issue/Bug-UAT | Link to Many table. Inflated results | D4 D5 | 1 | 3 |  | 0
Notin D5
HVC | HVC-PL-5 | Plant | Plant SOM | Plant Standard Operating Metrics | % Capacity Plant Feed Rate | % Capacity Plant Feed Rate | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to D5-Critical Issue/Bug-UAT | Under review. Not aligned with SOM Intent. | D4 D5' | 0 |  |  | 0
HVC | HVC-PL-23 HVC-PL-5B | Plant | Plant SOM | Plant Standard Operating Metrics | % Capacity Plant Production Rate | % Capacity Plant Production Rate | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to D5-Critical Issue/Bug-UAT | Under review. Not aligned with SOM Intent. | D4 D5' | 0 |  |  | 0
HVC | HVC-PL-45 | Plant | Plant SOM | Plant Standard Operating Metrics | Best Daily Feed Rate | Best Daily Feed Rate | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to D5-Critical Issue/Bug-UAT | Under review. Not aligned with SOM Intent. | D4 D5' | 0 |  |  | 0
HVC | HVC-PL-13 | Plant | Plant SOM | Plant Standard Operating Metrics | Best Daily Production Rate | Best Daily Production Rate | R5 | Metric | PARCview | 8 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to D5-Critical Issue/Bug-UAT | Under review. Not aligned with SOM Intent. | D4 D5' | 0 |  |  | 0
RDM | RDM-FI-3 | Finance | Finance | Finance General Ledger | Site Cash Production Cost (Actual) | Site Cash Production Cost (Actual) | R5 | Metric | Gencid | 8 | Robin Bailes | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Move to D5-Critical Issue/Bug-UAT | Link to Many table. Inflated results | D4 D5 |  |  |  |  | Pulled ones from Oriaze #1 Mar 15. Note not approved.
RDM | RDM-FI-4 | Finance | Finance | Finance General Ledger | Total Costs (Actual) | Total Costs (Actual) | R5 | Metric | Gencid | 8 | Robin Bailes | 0.25 | UAT Feb 17th (to Feb 21) | No |  | 1 | Move to D5-Critical Issue/Bug-UAT | Link to Many table. Inflated results | D4 D5 |  |  |  |  | Pulled ones from Oriaze #1 Mar 15. Note not approved.
CDA | CDA-PL-44 | Plant | Plant | Plant Assay | Recovery % - Cu | Recovery % - Cu | R3 | KPI | PIS | 3 | Miguel Vargas Romero | 0.25 | Complete- Dec 1 & 10 | Yes | No | 1 | Move to D5-Critical Issue/Bug-UAT | Formula Issue. W Gerry | D4 D5 | 1 | 1
RDM | RDM-PL-5b | Plant | Plant | Plant Standard Operating Metrics | Plant Production Rate % Capacity Plant Production Rate | % Capacity Plant Production Rate | R3 | KPI | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | TBC | Yes | See Note | 1 | Move to D5-Critical Issue/Bug-UAT | Under review. Not aligned with SOM Intent. | D4 D5 | de
Deployed but Hidden Require Fixing
RDM | RDM -PL-5 | Plant | Plant SOM | Plant Standard Operating Metrics | % Capacity Plant Feed Rate | % Capacity Plant Feed Rate | R5 | Metric | [11 empty] | 0 |  |  | 0
RDM | RDM -PL-13 | Plant | Plant SOM | Plant Standard Operating Metrics | Best Daily Production Rate | Best Daily Production Rate | R5 | Metric | [11 empty] | 0 |  |  | 0
Not sure where this one is at
RDM | RDM-PL-45 | Plant | Plant SOM | Plant Standard Operating Metrics | Best Daily Feed Rate | Best Daily Feed Rate | R5 | Metric | [11 empty] | 0 |  |  | 0
33
Pulled ones from Oriaze #1 Mar 3. Note not approved.
2023-03-03
[5 empty] | Remove | Keep
| 1 |  |  |  | Compliance Utilization
| 2 |  |  |  | Work Index (Corrected) | Work Index
| 3 |  |  |  | Non-scheduled Maintenance WO hours Complete-Mill | Total Break-in Hours (Actual)
| 4 |  |  |  | Scheduled Maintenance WO Hours | Total Hours (Scheduled)
| 5 |  |  |  | Scheduled Maintenance WO Hours completed | Total Non Break-in Hours Actual
| 6 |  |  |  | Schedule Load (Actual) | Schedule Load Available
Already Deployed Impacted
| HVC-WO-1 |  |  |  | Scheduled Maintenance WO Hours
Pulled ones from Oriaze #2. Note not approved.
RDM | RDM-PL-27 | Plant | Plant | Plant Downtime | Total Stream Event Count | Total Stream Event Count | R3 | Metric | GenCID | 4 | Randy Lewelellen/Robin Bailes | 0.25 | UAT Dec | Yes | No | 1 | Recommend De-scope | Source Data Issue. Genid stores combined | Recommend De-scope
HVC | HVC-PL-17 | Plant Standard Operating Metrics | Plant | Plant SOM | Plant Maintenance Internal Labor Hours | Plant Maintenance Internal Labor Hours | R5 | Metric | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to Backlog | Jacob. Deffer | Move to Backlog
HVC | HVC-PL-22 | Plant Standard Operating Metrics | Plant | Plant SOM | Plant Labor Factor (Internal Labor Factor) | Plant Labor Factor (Internal Labor Factor) | R5 | KPI | PARCview | 7 | Bruno/Frank | 0.25 | UAT Feb 16th (to Feb 21) | No |  | 1 | Moved to Backlog | Jacob. Deffer | Move to Backlog
HVC | HVC-WO-80 | Compliance and Workorder | Compliance | Compliance | Schedule Load (Actual) - Mill |  | R2 | KPI | JDE (Maintenance) | 2 | Paul Sundher/James Anderson | 0.25 | Nov 22 & Nov 23 | Yes | No | 1 | Deffered | Name issue | TBD
HVC | HVC-PL-34 | Plant | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade |  | R3 | Metric | PARCview | 4 | Frank Laroche | 0.25 | Complete | No | No | 1 | Critical Issue/Bug-PreUAT | Deffered Source Issue-HVC is updating their tags so once complete this can be retested (Two week outage with the site) Update: Postponed unitl site Changes Source | TBD
| RDM-PL-14-RT | Plant | Plant Standard Operating Metrics | Number of Maintenance Events
Add Pushed Metrics
67
D6 (March )-Dec Road Map
| HVC Maximo | Compliance | 36
|  | Work order | 9
| HVC Finance (Checking) |  | 5
| HVC | HVC-FI-20a | Finance | Finance General Ledger | Maintenance Department Site Cash Production Cost (Actual) | Metric | Cost Datamart
| HVC | HVC-FI-3a | Finance | Finance General Ledger | Site Cash Production Cost (Actual) | Metric | Cost Datamart
| HVC | HVC-FI-1 | Finance | Finance General Ledger | Maintenance Repair Cost (Actual) | Metric | JDE (Cost)
| HVC | HVC-FI-11 | Finance | Finance Planning | Maintenance Repair Cost (Budget) | Metric | JDE (Cost)
| HVC | HVC-FI-12 | Finance | Finance Planning | Maintenance Repair Cost (Forecast) | Metric | JDE (Cost)
|  |  | Abhi | KPI Catalouge
| QB Maximo -WO/Compliance | Compliance | 32 | 30 | Don Confirming 2 | QB2-WO/C-49 | D7
| RDM | 31
|  | 5 Finanace |  |  |  | QB2-WO/C-53 | No Deployment
2 Down Times
|  | Work Order | 0 | 8
|  | QB2 | Work Order | Work Order | QB2-WO-C-18 | Metric | # Non-scheduled Maintenance WO Completed - Mine
|  | QB2 | Work Order | Work Order | QB2-WO-C-19 | Metric | # Non-Scheduled Maintenance WO Completed due to Failure - Mine
|  | QB2 | Work Order | Work Order | QB2-WO-C-14 | Metric | # PMs Completed as Scheduled - Mine
|  | QB2 | Work Order | Work Order | QB2-WO-C-13 | Metric | # PMs Scheduled - Mine
|  | QB2 | Work Order | Work Order | QB2-WO-C-16 | Metric | # Scheduled Maintenance WO - Mine
|  | QB2 | Work Order | Work Order | QB2-WO-C-17 | Metric | # Scheduled Maintenance WO Completed - Mine
|  | QB2 | Work Order | Work Order | QB2-WO-C-15 | Metric | # Total Maintenance WO Completed - Mine
|  | QB2 | Work Order | Work Order | QB2-WO-C-10 | Metric | Mine Maintenance Internal labor Hours
|  |  | 35 | Source Not Landed
| QB Maximo HVC-WO/Compliance |  | 35 | Source Not Landed
| HVC Finance-Maximo/Cost Mart (History if Required JDE) |  | 18 | Source Landing Completion/Validation -Req | Oriaze had 3. Reconicilation Required
| CDA Finance- JDE |  | 5 | Source Validation Req
D5 (April)-Dec Road Map
Note on G82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Stuart BartonSuspect incorrect AS-IS built name. Should be Plant Production Rate, same as RDM-PL-23. @Oriaze Isoa @Gerry Beitel @Fahim Kanji

## Definitions
Defect | A defect is a shortcoming, an imperfection or a flaw in any system, which deviates the actual result from the expected one. Moreover, when the result does not meet the requirements or expectations of the end user, it is termed as a defect
Critical Defect | Showstopper, the system cannot function without the change. These defects result in complete failure. •An issue that effects a central/Critical requirement/ Critical Functionality. •No workaround identified. •Test execution cannot proceed until the defect is resolved. •Deployment to production cannot proceed due to a defect.
Major (High) | A major defect is that which collapses or crashes the system and yet there are a few functionalities that remain operable. A workaround in such cases is not impossible but it is very difficult. •An issue that impacts one of the important features/functions. •Workaround is identified but not accepted by the business. •Not all the test execution is halted due to the issue. •Deployment to production cannot proceed with business agreement.
Minor (Medium) | Such defects have an impact on the less important data and minor functions. It can cause some malfunction but will still keep the software up and running. The workaround is easy and obvious. •An issue that impacts a non-critical feature/functionality. •Workaround is identified and received business agreement. •Test execution can proceed with the defect in place. •Deployment to production can proceed with the approvals from the key stakeholders.
Trivial (Low) | These errors do not relate to the data or working of the software. In fact, trivial errors are those that relate to the look and feel of the program. These errors do not cause malfunctions by impacting any data or function. •An issue that is impacting a non-critical functionality/feature. •Cosmetic in nature and no adverse effect. •Test execution can proceed with this defect in place. •Deployment can proceed with the defect in place.
Severity | The impact that a defect has on either the development or execution of MARS BM. It is the degree of impact that the defect has, on the application.

## Spanish-Summary (hidden)
MARS for BM Testing Summary
R1 - 3 KPI Tracking | Current | %
Data Landing Testing | #REF! | #REF!
Business Owner/ Data Steward Validation | #REF! | #REF!
Unit Testing | #REF! | #REF!
Equation Testing | #REF! | #REF!
Business Rule testing | #REF! | #REF!
High or Critical Defect - Project/T&I Issue | #REF! | #REF!
High or Critical Defect - Source Data Issue | #REF! | #REF!
Ready for Pre-UAT | #REF! | #REF!
Pre-UAT | #REF! | #REF!
UAT | #REF! | #REF!
Deployed to Production | 0 | 0%
Total KPIs | 102
|  |  | R1 - 3 KPI Tracking | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | Delta | PreUAT needs to be updated
|  |  | Data Landing Testing | 56.73% | 56.73% | 82% | 82% | 82% | [5 empty] | 0% | Dashboard formulas are not changing
|  |  | Business Owner/ Data Steward Validation | 0% | 0% | 42.31% | 51% | 74% | [5 empty] | 23%
|  |  | Unit Testing | 56.73% | 56.73% | 59.62% | 82% | 82% | [5 empty] | 0% | CDA and RDO CloudIO testing complete, data issues being documented by Barb (Low & med), Pre-UAT testing to proceed with the identification of the known issues
|  |  | Equation Testing | 66.35% | 71.15% | 75% | 76% | 76% | [5 empty] | 0%
|  |  | Business Rule testing | 23.08% | 29.81% | 53.85% | 74% | 76% | [5 empty] | 2%
|  |  | High or Critical Defect - Project/T&I Issue | 14 | 9 | 9 | 3 | 0 | [5 empty] | -3
|  |  | High or Critical Defect - Source Data Issue | 22 | 17 | 18 | 18 | 18 | [5 empty] | 0
|  |  | Ready for Pre-UAT | 0% | 0% | 32.69% | 48% | 50% | [5 empty] | 2%
|  |  | Pre-UAT | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0%
|  |  | UAT | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0%
|  |  | Deployed to Production | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0%
There are 102 KPI's to be delivered for R1 - 3
|  |  |  | 40.58% | 42.88% | 62.55% | 73% | 78%
16.67%
Site changed their shift start and end times a number of times in February 2022. The CloudIO logic that calculates some status information uses the configured shift time in order to provide a clean timeline and as such, it applied some of it's business rules incorrectly in context of the data prior to March 2022. Data after March 2022 is unaffected.
We've engaged with site but they are unable to confirm the time ranges for shift changes, we're currently working to extrapolate that information and plan a resolution to correct the historical data.
Data after March 2022 is ready to move to the next stage of testing. Update for historical data will take a bit of time (potentially up to 6 weeks but not confirmed, we think that window is about the same whether we fix in CloudIO or Mars.)
This is the key item where we can deliver a window of data and start getting some value of data and then iterate to deliver the full history in the future if the team is onboard with that approach.
Craig Yelliga - ETA ~Sept 14
* Additional testing resource required Start date: asap -Dec 2022
|  |  | R1 - 3 KPI Tracking | 2022-08-26 | 2022-09-02 | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28
|  |  | Data Landing Testing | 2022-08-26: 59; 2022-09-02: 59; 2022-09-09: 82
|  |  | Business Owner/ Data Steward Validation | 2022-08-26: 0; 2022-09-02: 0; 2022-09-09: 0
|  |  | Unit Testing | 2022-08-26: 59; 2022-09-02: 59; 2022-09-09: 59
|  |  | Equation Testing | 2022-08-26: 69; 2022-09-02: 74; 2022-09-09: 75
|  |  | Business Rule testing | 2022-08-26: 24; 2022-09-02: 31; 2022-09-09: 53
|  |  | High or Critical Defect - Project/T&I Issue | 2022-08-26: 15; 2022-09-02: 9; 2022-09-09: 9
|  |  | High or Critical Defect - Source Data Issue | 2022-08-26: 23; 2022-09-02: 18; 2022-09-09: 18
|  |  | Ready for Pre-UAT | 2022-08-26: 13; 2022-09-02: 17; 2022-09-09: 0
|  |  | Pre-UAT | 2022-08-26: 0; 2022-09-02: 0; 2022-09-09: 0
|  |  | UAT | 2022-08-26: 0; 2022-09-02: 0; 2022-09-09: 0
|  |  | Deployed to Production | 2022-08-26: 0; 2022-09-02: 0; 2022-09-09: 0
#REF!
-
Pruebas
Pruebas con Usuarios
Producción
#REF!
0
#REF!
-3
Defectos
#REF!
+23%
#REF!
-
#REF!
-
#REF!
+2%
#REF!
+2%
#REF!
-
#REF!
-
0%
-
Pruebas
con el aterrizaje de datos
Validación de la data por el negocio
Pruebas de unidades de desarrollo
Pruebas de las formulas
Pruebas de las reglas del negocio
Listo para pruebas con usuarios
Antes de pruebas con usuarios
En
Producción
Pruebas con usuarios
Defectos
Proyecto/
Problema deT&I
Defectos relacionados con fuente de data

## Transformed Data
IMPORTANT DETAIL
In order to insert the PivotTable you selected, we had to organize your data in columns with a single header row.
| Release | RG | Site | KPI ID # | KPI Category | KPI Sub Category | KPI / Metric | Type | Source System | Cloud IO/DES Source data = Landing Zone, Data validation, Sustainment Plan Prod Delta Lake (not MARS) | Business Owner/ Data Steward Validation | MARS Build Team Unit Testing, Landing zone = Core data DEV & QA Env | MARS Testing, Product Team System Testing (Functional & Non-Functional) Equations, business rules, core, cube = expected results QA Env | Field14 | Maintenance Team Validation QA Env | Maintenance Site(s) SME Validation, Business Acceptance UAT Env | Release Planned Date | Release Name | Comments
[10 empty] | Data Landing Testing | Validation | Unit Testing | Equation Testing | Business Rule Testing | Pre-UAT | UAT
| R1 | R1-3 | RDM | RDM-ME-12 | Mobile Equipment Avail. | Mobile Equipment Avail. | Box Factor | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
| R1 | R1-3 | RDM | RDM-ME-13 | Mobile Equipment Avail. | Mobile Equipment Avail. | Fleet Productivity | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
| R1 | R1-3 | RDM | RDM-ME-14 | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-15 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Down Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-16 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Failure Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-17 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Down (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-18 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Failure (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-19 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time To Repair (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-20 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mobile Availability (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-21 | Mobile Equipment Avail. | Mobile Equipment Avail. | Operating Efficiency (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-22 | Mobile Equipment Avail. | Mobile Equipment Avail. | Use of Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-33 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Operating Hours to First Down After PM | KPI | Cloud IO <35 days and >35 days | Testing Passed
| R1 | R1-3 | RDM | RDM-ME-34 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Down Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
| R1 | R1-3 | RDM | RDM-ME-35 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Failure Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
| R1 | R1-3 | RDM | RDM-ME-36 | Mobile Equipment Avail. | Mobile Equipment Avail. | Total Down Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
| R1 | R1-3 | RDM | RDM-ME-37 | Mobile Equipment Avail. | Mobile Equipment Avail. | Total Failure Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
| R1 | R1-3 | RDM | RDM-ME-38 | Mobile Equipment Avail. | Mobile SOM | Asset Down Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-39 | Mobile Equipment Avail. | Mobile SOM | Asset Event Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-40 | Mobile Equipment Avail. | Mobile SOM | Asset Failure Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-41 | Mobile Equipment Avail. | Mobile SOM | FMS Total Active Maintenance Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-42 | Mobile Equipment Avail. | Mobile SOM | FMS Total Available Time (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-43 | Mobile Equipment Avail. | Mobile SOM | FMS Total Excluded Calendar Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-44 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Delay Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-45 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-46 | Mobile Equipment Avail. | Mobile SOM | FMS Total Operational Delay Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-47 | Mobile Equipment Avail. | Mobile SOM | FMS Total Production Time (Hours) (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-48 | Mobile Equipment Avail. | Mobile SOM | FMS Total Standby Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | RDM | RDM-ME-49 | Mobile Equipment Avail. | Mobile SOM | FMS Total Utilized Time (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R1 | R1-3 | CDA | CDA-ME-12 | Mobile Equipment Avail. | Mobile Equipment Avail. | Box Factor | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
| R1 | R1-3 | CDA | CDA-ME-13 | Mobile Equipment Avail. | Mobile Equipment Avail. | Fleet Productivity | KPI | Cloud IO | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | As per SAM these fall under SHM and should not be part of MARS for BM Scope (DR21)
| R1 | R1-3 | CDA | CDA-ME-14 | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-15 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Down Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-16 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Failure Time (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-17 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Down (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-18 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time Between Failure (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-19 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mean Time To Repair (Hours) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-20 | Mobile Equipment Avail. | Mobile Equipment Avail. | Mobile Availability (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-21 | Mobile Equipment Avail. | Mobile Equipment Avail. | Operating Efficiency (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-22 | Mobile Equipment Avail. | Mobile Equipment Avail. | Use of Availability (Actual) | KPI | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-33 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Operating Hours to First Down After PM | KPI | Cloud IO <35 days and >35 days | Testing Passed
| R1 | R1-3 | CDA | CDA-ME-34 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Down Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
| R1 | R1-3 | CDA | CDA-ME-35 | Mobile Equipment Avail. | Mobile Equipment Avail. | Average Failure Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
| R1 | R1-3 | CDA | CDA-ME-27 | Mobile Equipment Avail. | Mobile Equipment Avail. | Maintenance Department Site Cash Production Cost Per Prod/Aux Operating Hours (Actual) | Metric | Cloud IO <35 days and >35 days
| R1 | R1-3 | CDA | CDA-ME-36 | Mobile Equipment Avail. | Mobile Equipment Avail. | Total Down Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
| R1 | R1-3 | CDA | CDA-ME-37 | Mobile Equipment Avail. | Mobile Equipment Avail. | Total Failure Count (First Hour) | Metric | Cloud IO <35 days and >35 days | Testing Passed
| R1 | R1-3 | CDA | CDA-ME-38 | Mobile Equipment Avail. | Mobile SOM | Asset Down Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-39 | Mobile Equipment Avail. | Mobile SOM | Asset Event Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-40 | Mobile Equipment Avail. | Mobile SOM | Asset Failure Count | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-41 | Mobile Equipment Avail. | Mobile SOM | FMS Total Active Maintenance Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-42 | Mobile Equipment Avail. | Mobile SOM | FMS Total Available Time (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-43 | Mobile Equipment Avail. | Mobile SOM | FMS Total Excluded Calendar Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-44 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Delay Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-45 | Mobile Equipment Avail. | Mobile SOM | FMS Total Maintenance Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-46 | Mobile Equipment Avail. | Mobile SOM | FMS Total Operational Delay Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-47 | Mobile Equipment Avail. | Mobile SOM | FMS Total Production Time (Hours) (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-48 | Mobile Equipment Avail. | Mobile SOM | FMS Total Standby Hours (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R1 | R1-3 | CDA | CDA-ME-49 | Mobile Equipment Avail. | Mobile SOM | FMS Total Utilized Time (Actual) | Metric | Cloud IO <35 days and >35 days | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R2 | R1-3 | HVC | HVC-WO-1 | Work Order | Work Order | Scheduled Maintenance WO Hours - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-2 | Work Order | Work Order | Scheduled Maintenance WO Hours Completed - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R2 | R1-3 | HVC | HVC-WO-3 | Work Order | Work Order | Non-scheduled Maintenance WO Hours Completed - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R2 | R1-3 | HVC | HVC-WO-4 | Work Order | Work Order | # PMs Scheduled - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R2 | R1-3 | HVC | HVC-WO-5 | Work Order | Work Order | # PMs Completed as Scheduled - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R2 | R1-3 | HVC | HVC-WO-6 | Work Order | Work Order | # Total Maintenance WO Completed - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R2 | R1-3 | HVC | HVC-WO-7 | Work Order | Work Order | # Scheduled Maintenance WO - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R2 | R1-3 | HVC | HVC-WO-8 | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R2 | R1-3 | HVC | HVC-WO-9 | Work Order | Work Order | # Non-scheduled Maintenance WO Completed - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R2 | R1-3 | HVC | HVC-WO-71 | Compliance | Compliance | Break-in Ratio (duration) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-76 | Compliance | Compliance | PM Schedule Compliance (By Duration) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-77 | Compliance | Compliance | PM Schedule Compliance (By Work Order Count) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R2 | R1-3 | HVC | HVC-WO-78 | Compliance | Compliance | Schedule Compliance (By Duration) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-79 | Compliance | Compliance | Schedule Compliance (By Work Order Count) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-80 | Compliance | Compliance | Schedule Load (Actual) - Mill | KPI | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Deferred |  |  | Deferred to future release
| R2 | R1-3 | HVC | HVC-WO-83 | Compliance | Compliance | Total Break-In Hours (Actual) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-85 | Compliance | Compliance | Total Distinct Work Order Count - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-86 | Compliance | Compliance | Total Hours (Actual) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-88 | Compliance | Compliance | Total Hours (Scheduled) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-97 | Compliance | Compliance | Total Non Break-In Hours (Actual) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-98 | Compliance | Compliance | Total Non Break-In PM Hours (Actual) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-99 | Compliance | Compliance | Total PM Hours (Scheduled) - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | HVC | HVC-WO-103 | Compliance | Compliance | Total Work Order Count - Mill | Metric | JDE (Maintenance) | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-45 | Compliance | Compliance | Total Hours (Actual) - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-86 | Compliance | Compliance | Total Hours (Actual) - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R3 | R1-3 | HVC | HVC-PL-30 | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4
| R3 | R1-3 | HVC | HVC-PL-31 | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4
| R3 | R1-3 | HVC | HVC-PL-32 | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4
| R3 | R1-3 | HVC | HVC-PL-33 | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4
| R3 | R1-3 | HVC | HVC-PL-34 | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade | Metric | PARCview | Data Source is changing | Data Source is changing | [7 empty] | HVC is updating their tags so once complete this can be retested (Two week outage with the site), it will be tested after the Source system is replaced at the HVC site.
| R3 | R1-3 | HVC | HVC-PL-35 | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4
| R3 | R1-3 | HVC | HVC-PL-38 | Plant | Plant Production Metrics | Total Metal (Adjusted) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4
| R3 | R1-3 | HVC | HVC-PL-40 | Plant | Plant Production Metrics | Total ore (Adjusted) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4
| R2 | R1-3 | RDM | RDM-WO/C-4 | Work Order | Work Order | # PMs Scheduled - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-6 | Work Order | Work Order | # Total Maintenance WO Completed - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-7 | Work Order | Work Order | # Scheduled Maintenance WO - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-8 | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | Metric | GenCID | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | Source data issue (excel is part of the data required and cannot be ingested). Moving to the backlog to remove from R1-3 deployment will be delivered in a future release. # Scheduled Maintenance WO Completed is blank because this needed to be created in conjunction with a spreadsheet as a source to get weekly schedule which is not available from the source system. You are right to see data for #scheduled maintenance WO and #total maintenance WO completed as those are the count of work orders in scheduled and completed statuses respectively. The combination of both does not give #scheduled maintenance WO completed as this kpi is for work orders that are completed as scheduled, and since we don’t have spreadsheets ingested, this is blank.
| R2 | R1-3 | RDM | RDM-WO/C-13 | Work Order | Work Order | # PMs Scheduled - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-15 | Work Order | Work Order | # Total Maintenance WO Completed - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-16 | Work Order | Work Order | # Scheduled Maintenance WO - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-17 | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mine | Metric | GenCID | Remove | Remove | Remove | Remove | Remove | Remove | Remove |  |  | Source data issue (excel is part of the data required and cannot be ingested). Moving to the backlog to remove from R1-3 deployment will be delivered in a future release. # Scheduled Maintenance WO Completed is blank because this needed to be created in conjunction with a spreadsheet as a source to get weekly schedule which is not available from the source system. You are right to see data for #scheduled maintenance WO and #total maintenance WO completed as those are the count of work orders in scheduled and completed statuses respectively. The combination of both does not give #scheduled maintenance WO completed as this kpi is for work orders that are completed as scheduled, and since we don’t have spreadsheets ingested, this is blank.
| R2 | R1-3 | RDM | RDM-WO/C-44 | Compliance | Compliance | Total Distinct Work Order Count - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-62 | Compliance | Compliance | Total Work Order Count - Mine | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-85 | Compliance | Compliance | Total Distinct Work Order Count - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R2 | R1-3 | RDM | RDM-WO/C-103 | Compliance | Compliance | Total Work Order Count - Mill | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | D1 | In Production
| R3 | R1-3 | RDM | RDM-PL-1 | Plant | Plant Standard Operating Metrics | Effective Asset Utilization | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-2 | Plant | Plant Standard Operating Metrics | Maintenance Availability | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-3 | Plant | Plant Standard Operating Metrics | Mean Down Time (Hours) | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-4 | Plant | Plant Standard Operating Metrics | Mean Time Between Downs (Hours) | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-5 | Plant | Plant Standard Operating Metrics | % Capacity | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-6 | Plant | Plant Standard Operating Metrics | Physical Availability | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-7 | Plant | Plant Standard Operating Metrics | % Online Time | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  | 2023-02-28 | D4
| R3 | R1-3 | RDM | RDM-PL-9 | Finance | Plant Standard Operating Metrics | Plant Department Site Cash Production Cost Per Monthly Plant Operating Hours (Actual) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | In Progress | 2023-02-28 | D4 | 643106 - High, with Build Team, ETA - 13 Feb
| R3 | R1-3 | RDM | RDM-PL-12 | Plant | Plant Standard Operating Metrics | Daily Production Rate When Running | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-13 | Plant | Plant Standard Operating Metrics | Best Daily Production Rate | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-14 | Plant | Plant Standard Operating Metrics | Number of Maintenance Events | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | Out of Scope
| R3 | R1-3 | RDM | RDM-PL-15 | Plant | Plant Standard Operating Metrics | Tonnes Processed (Total Milled in SMT) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-21 | Plant | Plant Standard Operating Metrics | Plant Feed Rate | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-26 | Plant | Plant Downtime | Total Stream Downtime (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-27 | Plant | Plant Downtime | Total Stream Event Count | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R3 |  | RDM | RDM-PL-5b | Plant | Plant Standard Operating Metrics | % Capacity Plant Production Rate | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4
| R3 | R1-3 | RDM | RDM-PL-30 | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-31 | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-32 | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-33 | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-34 | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-35 | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-36 | Plant | Plant Production Metrics | Plant Yield (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-38c | Plant | Plant Production Metrics | Total Metal - Zinc + Lead (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-39c | Plant | Plant Production Metrics | Total Metal - Zinc + Lead (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-40 | Plant | Plant Production Metrics | Total ore (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-41 | Plant | Plant Production Metrics | Total ore (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 |  | RDM | RDM-PL-47 | Plant | Plant Standard Operating Metrics | Total Number of Downs | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-48 | Plant | Plant Standard Operating Metrics | Available Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-49 | Plant | Plant Standard Operating Metrics | Calendar Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-50 | Plant | Plant Standard Operating Metrics | Excluded Calendar Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-51 | Plant | Plant Standard Operating Metrics | Maintenance Non Scheduled (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-52 | Plant | Plant Standard Operating Metrics | Maintenance Scheduled (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-53 | Plant | Plant Standard Operating Metrics | Maintenance Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-54 | Plant | Plant Standard Operating Metrics | Major Maintenance Shutdown (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-55 | Plant | Plant Standard Operating Metrics | Operating Delays (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-56 | Plant | Plant Standard Operating Metrics | Production Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-57 | Plant | Plant Standard Operating Metrics | Standby Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-58 | Plant | Plant Standard Operating Metrics | Utilized Time (Hours) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | CDA | CDA-PL-30 | Plant | Plant Assay | Copper Tails Grade (Zinc Tails Grade) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R3 | R1-3 | CDA | CDA-PL-31 | Plant | Plant Assay | Copper Conc Produced (Zinc Conc Produced) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R3 | R1-3 | CDA | CDA-PL-32 | Plant | Plant Assay | Copper Contained in Cu Conc (Zinc Contained in Zinc Conc) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R3 | R1-3 | CDA | CDA-PL-33 | Plant | Plant Assay | Copper Conc Mo Grade \ Zinc Con Pb Grade | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R3 | R1-3 | CDA | CDA-PL-34 | Plant | Plant Assay | Copper Conc Insol Grade \ Zinc Conc. Ag Grade | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R3 | R1-3 | CDA | CDA-PL-35 | Plant | Plant Production Metrics | Plant Yield (Adjusted) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R3 | R1-3 | CDA | CDA-PL-38 | Plant | Plant Production Metrics | Total Metal (Adjusted) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R3 | R1-3 | CDA | CDA-PL-40 | Plant | Plant Production Metrics | Total ore (Adjusted) | Metric | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2022-12-08 | D2 | In Production
| R3 |  | RDM | RDM-PL-38 | Plant | Plant Production Metrics | Total Metal Zinc (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 |  | RDM | RDM-PL-39 | Plant | Plant Production Metrics | Total Metal Zinc (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-38b | Plant | Plant Production Metrics | Total Metal Lead (Adjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-39b | Plant | Plant Production Metrics | Total Metal Lead (Unadjusted) | Metric | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-23 | Plant | Plant Standard Operating Metrics | Plant Production Rate | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | HVC | HVC-PL-44 | Plant | Plant Assay | Recovery % - Cu | KPI | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-02-28 | D4
| R3 | R1-3 | RDM | RDM-PL-44a | Plant | Plant Assay | Recovery % - Zn | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | RDM | RDM-PL-44b | Plant | Plant Assay | Recovery % - Pb | KPI | GenCID | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | 2023-01-26 | D3 | In Production
| R3 | R1-3 | CDA | CDA-PL-44 | Plant | Plant Assay | Recovery % - Cu | KPI | PIS | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress | 2023-02-28 | D4 | Gerry to confirm
| R5 | R5 | HVC | HVC-PL-22 | Plant SOM | Plant Standard Operating Metrics | Plant Labor Factor (Internal Labor Factor) | KPI | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-17 | Plant SOM | Plant Standard Operating Metrics | Plant Maintenance Internal Labor Hours | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-47 | Plant SOM | Plant Standard Operating Metrics | Total Number of Downs | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-48 | Plant SOM | Standard Time Definitions | Available Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-49 | Plant SOM | Standard Time Definitions | Available Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-50 | Plant SOM | Standard Time Definitions | Available Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-51 | Plant SOM | Standard Time Definitions | Maintenance Non Scheduled (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-52 | Plant SOM | Standard Time Definitions | Maintenance Scheduled (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-53 | Plant SOM | Standard Time Definitions | Maintenance Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-54 | Plant SOM | Standard Time Definitions | Major Maintenance Shutdown (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-55 | Plant SOM | Standard Time Definitions | Operating Delays (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-56 | Plant SOM | Standard Time Definitions | Production Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-57 | Plant SOM | Standard Time Definitions | Standby Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-58 | Plant SOM | Standard Time Definitions | Utilized Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-5 | Plant SOM | Plant Standard Operating Metrics | % Capacity Plant Feed Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | High or Critical Defect - Project/T&I Issue |  | 2023-02-28 | D4 | 654219 - High, with Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-PL-5b | Plant SOM | Plant Standard Operating Metrics | % Capacity Plant Production Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | High or Critical Defect - Project/T&I Issue |  | 2023-02-28 | D4 | 654219 - High, with Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-PL-7 | Plant SOM | Plant Standard Operating Metrics | % Online Time | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-45 | Plant SOM | Plant Standard Operating Metrics | Best Daily Feed Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-13 | Plant SOM | Plant Standard Operating Metrics | Best Daily Production Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-46 | Plant SOM | Plant Standard Operating Metrics | Daily Feed Rate When Running | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-12 | Plant SOM | Plant Standard Operating Metrics | Daily Production Rate When Running | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-1 | Plant SOM | Plant Standard Operating Metrics | Effective Asset Utilization | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-2 | Plant SOM | Plant Standard Operating Metrics | Maintenance Availability | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-3 | Plant SOM | Plant Standard Operating Metrics | Mean Down Time (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-4 | Plant SOM | Plant Standard Operating Metrics | Mean Time Between Downs (Hours) | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-14 | Plant SOM | Plant Standard Operating Metrics | Number of Maintenance Events | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | High or Critical Defect - Project/T&I Issue |  |  |  | Out of Scope
| R5 | R5 | HVC | HVC-PL-6 | Plant SOM | Plant Standard Operating Metrics | Physical Availability | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-21 | Plant SOM | Plant Standard Operating Metrics | Plant Feed Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-PL-23 | Plant SOM | Plant Standard Operating Metrics | Plant Production Rate | Metric | PARCview | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | HVC | HVC-ME-38 | Mobile SOM | Mobile Equipment Avail. | Asset Down Count | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-39 | Mobile SOM | Mobile Equipment Avail. | Asset Event Count | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-40 | Mobile SOM | Mobile Equipment Avail. | Asset Failure Count | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-41 | Mobile SOM | Mobile Equipment Avail. | FMS Total Active Maintenance Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-42 | Mobile SOM | Mobile Equipment Avail. | FMS Total Available Time (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-43 | Mobile SOM | Mobile Equipment Avail. | FMS Total Excluded Calendar Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-44 | Mobile SOM | Mobile Equipment Avail. | FMS Total Maintenance Delay Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-45 | Mobile SOM | Mobile Equipment Avail. | FMS Total Maintenance Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-46 | Mobile SOM | Mobile Equipment Avail. | FMS Total Operational Delay Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-47 | Mobile SOM | Mobile Equipment Avail. | FMS Total Production Time (Hours) (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-48 | Mobile SOM | Mobile Equipment Avail. | FMS Total Standby Hours (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-49 | Mobile SOM | Mobile Equipment Avail. | FMS Total Utilized Time (Actual) | Metric | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-14 | Mobile Equipment Avail. | Mobile Equipment Avail. | FMS Maintenance Availability (Actual) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-15 | Mobile Equipment Avail. | Mobile Equipment Avail. | FMS Mean Down Time (Hours) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-16 | Mobile Equipment Avail. | Mobile Equipment Avail. | FMS Mean Failure Time (Hours) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-17 | Mobile Equipment Avail. | Mobile Equipment Avail. | FMS Mean Time Between Down (Hours) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-18 | Mobile Equipment Avail. | Mobile Equipment Avail. | FMS Mean Time Between Failure (Hours) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-19 | Mobile Equipment Avail. | Mobile Equipment Avail. | FMS Mean Time To Repair (Hours) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-20 | Mobile Equipment Avail. | Mobile Equipment Avail. | FMS Mobile Availability (Actual) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-21 | Mobile Equipment Avail. | Mobile Equipment Avail. | FMS Operating Efficiency (Actual) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | HVC | HVC-ME-22 | Mobile Equipment Avail. | Mobile Equipment Avail. | FMS Use of Availability (Actual) | KPI | Wenco | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed |  |  | 2023-02-28 | D4 | 653361 - Medium, 653367 - Medium, With Build Team, ETA - 13 Feb
| R5 | R5 | RDM | RDM-FI-20 | Finance | Finance Planning | Maintenance Department Site Cash Production Cost (Actual) | Metric | Gencid | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | RDM | RDM-FI-2 | Finance | Finance Planning | Plant Department Site Cash Production Cost (Actual) | Metric | Gencid | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | RDM | RDM-FI-3 | Finance | Finance General Ledger | Site Cash Production Cost (Actual) | Metric | Gencid | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 | R5 | RDM | RDM-FI-4 | Finance | Finance General Ledger | Total Costs (Actual) | Metric | Gencid | Testing Passed | Testing Passed | Testing Passed | Testing Passed | Testing Passed | In Progress |  | 2023-02-28 | D4
| R5 |  | RDM | RDM-PL-26-RT | Plant | Plant Downtime | Total Stream Downtime (Hours) | Metric | RT-DUET | [7 empty] | 2023-03-31 | D5
| R5 |  | RDM | RDM-PL-27-RT | Plant | Plant Downtime | Total Stream Event Count | Metric | RT-DUET | [7 empty] | 2023-03-31 | D5
| R5 |  | RDM | RDM-PL-51-RT | Plant | Plant Standard Operating Metrics | Maintenance Non Scheduled (Hours) | Metric | RT-DUET | [7 empty] | 2023-03-31 | D5
| R5 |  | RDM | RDM-PL-52-RT | Plant | Plant Standard Operating Metrics | Maintenance Scheduled (Hours) | Metric | RT-DUET | [7 empty] | 2023-03-31 | D5
| R5 |  | RDM | RDM-PL-53-RT | Plant | Plant Standard Operating Metrics | Maintenance Time (Hours) | Metric | RT-DUET | [7 empty] | 2023-03-31 | D5
| R5 |  | RDM | RDM-PL-54-RT | Plant | Plant Standard Operating Metrics | Major Maintenance Shutdown (Hours) | Metric | RT-DUET | [7 empty] | 2023-03-31 | D5
| R5 |  | RDM | RDM-PL-55-RT | Plant | Plant Standard Operating Metrics | Operating Delays (Hours) | Metric | RT-DUET | [7 empty] | 2023-03-31 | D5
| R5 |  | RDM | RDM-PL-57-RT | Plant | Plant Standard Operating Metrics | Standby Time (Hours) | Metric | RT-DUET | [7 empty] | 2023-03-31 | D5
| R5 |  | RDM | RDM-PL-47-RT | Plant | Plant Standard Operating Metrics | Total Number of Downs | Metric | RT-DUET | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-30 | Compliance | Compliance | Break-in Ratio (duration) - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-34 | Compliance | Compliance | Failure Break-In Ratio - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-35 | Compliance | Compliance | Non Failure Break-In Ratio - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-36 | Compliance | Compliance | PM Schedule Compliance (By Duration) - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-37 | Compliance | Compliance | PM Schedule Compliance (By Work Order Count) - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-38 | Compliance | Compliance | Schedule Compliance (By Duration) - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-39 | Compliance | Compliance | Schedule Compliance (By Work Order Count) - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-40 | Compliance | Compliance | Schedule Load (Actual) - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-41 | Compliance | Compliance | Schedule Load (Available) - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-64 | Compliance | Compliance | Work Index - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-65 | Compliance | Compliance | Work Index (Corrected) - Mine | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-24 | Compliance | Compliance | Average Compliance Days - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-25 | Compliance | Compliance | Average Compliance Meter Hours - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-42 | Compliance | Compliance | Total Break-In Failure Hours (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-43 | Compliance | Compliance | Total Break-In Hours (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-44 | Compliance | Compliance | Total Break-In Non Failure Hours (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-45 | Compliance | Compliance | Total Distinct Work Order Count - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-46 | Compliance | Compliance | Total Hours (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-47 | Compliance | Compliance | Total Hours (Available) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-48 | Compliance | Compliance | Total Hours (Scheduled) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-57 | Compliance | Compliance | Total Non Break-In Hours (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-58 | Compliance | Compliance | Total Non Break-In PM Hours (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-59 | Compliance | Compliance | Total PM Hours (Scheduled) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-63 | Compliance | Compliance | Total Work Order Count - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-49 | Compliance | Item and Trade | Total Item Break-In Cost (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-49-MA | Compliance | Item and Trade | Total Item Break-In Cost (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-50 | Compliance | Item and Trade | Total Item Cost (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-51 | Compliance | Item and Trade | Total Item Cost (Budget) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-52 | Compliance | Item and Trade | Total Item Quantity (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-53 | Compliance | Item and Trade | Total Item Quantity (Resource) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-102-MA | Compliance | Item and Trade | Total Trade Cost (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | QB | QB2-WO/C-103-MA | Compliance | Item and Trade | Total Trade Cost (Budget) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-71-MA | Compliance | Compliance | Break-in Ratio (duration) - Mill | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-73-MA | Compliance | Compliance | Compliance Utilization - Mill | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-76-MA | Compliance | Compliance | PM Schedule Compliance (By Duration) - Mill | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-77-MA | Compliance | Compliance | PM Schedule Compliance (By Work Order Count) - Mill | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-78-MA | Compliance | Compliance | Schedule Compliance (By Duration) - Mill | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-79-MA | Compliance | Compliance | Schedule Compliance (By Work Order Count) - Mill | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-80-MA | Compliance | Compliance | Schedule Load (Actual) - Mill | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-81-MA | Compliance | Compliance | Schedule Load (Available) - Mill | KPI | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-65 | Compliance | Compliance | Average Compliance Days - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-27 | Compliance | Compliance | Average Meter Hours Difference - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-69 | Compliance | Compliance | Average Target Days - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-69-MA | Compliance | Compliance | Average Target Days - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-72-MA | Compliance | Compliance | Break-in Work (Count) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-83-MA | Compliance | Compliance | Total Break-In Hours (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-84 | Compliance | Compliance | Total Break-In Non Failure Hours (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-85-MA | Compliance | Compliance | Total Distinct Work Order Count - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-86-MA | Compliance | Compliance | Total Hours (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-88-MA | Compliance | Compliance | Total Hours (Scheduled) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-97-MA | Compliance | Compliance | Total Non Break-In Hours (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-98-MA | Compliance | Compliance | Total Non Break-In PM Hours (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-99-MA | Compliance | Compliance | Total PM Hours (Scheduled) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-103-MA | Compliance | Compliance | Total Work Order Count - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-89 | Compliance | Item and Trade | Total Item Break-In Cost (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-48 | Compliance | Item and Trade | Total Item Break-In Cost (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-90 | Compliance | Item and Trade | Total Item Cost (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-49 | Compliance | Item and Trade | Total Item Cost (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-91 | Compliance | Item and Trade | Total Item Cost (Budget) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-50 | Compliance | Item and Trade | Total Item Cost (Budget) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-92 | Compliance | Item and Trade | Total Item Quantity (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-51 | Compliance | Item and Trade | Total Item Quantity (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-100 | Compliance | Item and Trade | Total Trade Break-In Cost (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-59 | Compliance | Item and Trade | Total Trade Break-In Cost (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-101 | Compliance | Item and Trade | Total Trade Cost (Actual) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-60 | Compliance | Item and Trade | Total Trade Cost (Actual) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-102 | Compliance | Item and Trade | Total Trade Cost (Budget) - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-61 | Compliance | Item and Trade | Total Trade Cost (Budget) - Mine | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-9-MA | Work Order | Work Order | # Non-scheduled Maintenance WO Completed - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-5-MA | Work Order | Work Order | # PMs Completed as Scheduled - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-4-MA | Work Order | Work Order | # PMs Scheduled - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-7-MA | Work Order | Work Order | # Scheduled Maintenance WO - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-8-MA | Work Order | Work Order | # Scheduled Maintenance WO Completed - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-6-MA | Work Order | Work Order | # Total Maintenance WO Completed - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-3-MA | Work Order | Work Order | Non-scheduled Maintenance WO Hours Completed - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-1-MA | Work Order | Work Order | Scheduled Maintenance WO Hours - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-WO-2-MA | Work Order | Work Order | Scheduled Maintenance WO Hours Completed - Mill | Metric | Maximo | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-FI-20a | Finance | Finance General Ledger | Maintenance Department Site Cash Production Cost (Actual) | Metric | Cost Datamart | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-FI-3a | Finance | Finance General Ledger | Site Cash Production Cost (Actual) | Metric | Cost Datamart | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-FI-1 | Finance | Finance General Ledger | Maintenance Repair Cost (Actual) | Metric | JDE (Cost) | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-FI-11 | Finance | Finance Planning | Maintenance Repair Cost (Budget) | Metric | JDE (Cost) | [7 empty] | 2023-03-31 | D5
| R5 |  | HVC | HVC-FI-12 | Finance | Finance Planning | Maintenance Repair Cost (Forecast) | Metric | JDE (Cost) | [7 empty] | 2023-03-31 | D5
| R5 |  | RDM | RDM-PL-5b-RT | Plant | Plant Standard Operating Metrics | % Capacity Plant Production Rate | KPI | RT-DUET
| R5 | R1-3 | RDM | RDM-PL-5-RT | Plant | Plant Standard Operating Metrics | % Capacity Plant Feed Rate | KPI | RT-DUET
| R5 | R1-3 | RDM | RDM-PL-7-RT | Plant | Plant Standard Operating Metrics | % Online Time | KPI | RT-DUET
| R5 | R1-3 | RDM | RDM-PL-3-RT | Plant | Plant Standard Operating Metrics | Mean Down Time (Hours) | KPI | RT-DUET
| R5 | R1-3 | RDM | RDM-PL-4-RT | Plant | Plant Standard Operating Metrics | Mean Time Between Downs (Hours) | KPI | RT-DUET
| R5 | R1-3 | RDM | RDM-PL-12-RT | Plant | Plant Standard Operating Metrics | Daily Production Rate When Running | Metric | RT-DUET
| R5 | R1-3 | RDM | RDM-PL-13-RT | Plant | Plant Standard Operating Metrics | Best Daily Production Rate | Metric | RT-DUET
| R5 | R1-3 | RDM | RDM-PL-48-RT | Plant | Plant Standard Operating Metrics | Available Time (Hours) | Metric | RT-DUET
| R5 | R1-3 | RDM | RDM-PL-2-RT | Plant | Plant Standard Operating Metrics | Maintenance Availability | Metric | RT-DUET

## Sheet2
Release Name | (All)